## Dashboard
ADM FireNode Forest Monitoring Workbook - Dashboard
Living source of truth for the hybrid LoRa + Wi-Fi FireNode implementation. Update this workbook after every major completed step.
Total Steps
Done
In Progress
Blocked
Not Started
Completion
Current Stage | MAIN .51 dashboard is in LIVE mode. MAIN .51 CSI camera works. NODE_01 .52 CSI camera works and appears on MAIN dashboard. MAIN can discover/pull NODE_01 data. Remote node aggregation is working for .52. .53 and .54 are pending hardware build. Thermal camera is part of MAIN design but not physically installed yet. USB microphone/chainsaw detection is still pending. MAIN ESP32 USB serial integration has been implemented in code but is pending deployment/verification. MAIN ESP32 serial data was manually confirmed by Minicom on /dev/ttyUSB0 at 115200.
Next Action | Separate NODE GUI implemented: node_dashboard.html + node_app.js for NODE RPis only (192.168.9.52/.53/.54). NODE GUI is one-page only with local camera, sensor readings, chainsaw controls/status, alerts, recordings. MAIN server dashboard (dashboard.html + app.js) preserved unchanged. NODE simulation mode forced to live. Chainsaw controls moved to NODE dashboard. No ESP32/LoRa/thermal architecture changes.
Recommended Current Architecture
Layer | Recommended Implementation | Reason | Status | Owner | Date | Evidence | Notes
Topology | 4 Raspberry Pi field units: 1 center/main server node and 3 remote nodes | Matches client clarification and Zoom meeting | Approved | Codex/User | 2026-05-15 | User clarification 2026-05-13; Zoom transcript; FireDiagram.png | Main server is physically installed on the center/backup node.
Telemetry | LoRa for sensor readings, alerts, RSSI/SNR, and heartbeat packets | PDF and client meeting prioritize LoRa for range and sensor communication | Approved | Codex/User | 2026-05-15 | Details-protoLORA.pdf; Zoom transcript | Wi-Fi is not the canonical telemetry path.
Video | Wi-Fi for daytime camera feeds from every node and dashboard viewing | LoRa cannot carry camera streams; meeting allowed Wi-Fi for image/live view | Approved | Codex/User | 2026-05-15 | Zoom transcript and user clarification | All nodes and main server have their own daytime camera.
Thermal | Single MLX90640 on main/center server only | Latest user instruction overrides older 4-thermal-camera slide | Approved | User | 2026-05-15 | User clarification | Remote nodes do not include thermal camera in final design.
Audio | RPi-based chainsaw detector on node and main programs; improve current FFT/RMS detector | Existing ZIP has working detector.py and RPi can handle audio better than ESP32 | Approved | Codex | 2026-05-15 | firenode RPi ZIPs | Use ESP32 only for lightweight sensors and LoRa support.
Power | Each field unit uses 12V battery with fused buck conversion and battery telemetry | User clarified all nodes/main use 12V 40A batteries | Approved | User | 2026-05-15 | User clarification | Add voltage divider + low-voltage warning.

## README
ADM FireNode Implementation Workbook
How to use this workbook as the recovery reference if the chat breaks.
Topic | Workbook Rule | Why It Matters | Update Trigger | Owner
Source of truth | Workbook plus GitHub repository are the project memory | Allows continuation after chat loss | Every completed major step | Codex/User
Workbook updates | Update Progress Tracker, Change Log, Decision Log, and affected technical sheets | Keeps implementation traceable | After design, code, test, hardware, or deployment milestone | Codex
GitHub updates | Commit code and workbook together in the same logical change | Workbook always matches code state | After local verification | Codex/User
Hardware validation | Record physical results in Test Campaign and Issue Log | Codex cannot verify field hardware without user evidence | After each field bench/forest test | User
Repository status | Current ADM Fire folder is not a Git repository | Cannot push until repo/branch is provided | Before first GitHub sync | User
Artifact Sources Incorporated
Artifact | Path / Source | Used For | Important Notes
Details-protoLORA.pdf | /Users/.../ADM Fire/Details-protoLORA.pdf | Objectives, validation, LoRa, algorithms, component options | LoRa-first requirements and PDR >70%.
FireDiagram.png | /Users/.../ADM Fire/FireDiagram.png | Topology, dashboard, camera rules, siren | Older diagram mentioned 4 thermal modules; overridden.
RPi ZIP v4 | firenode_rpi_main_server_mlx90640_v4_2_three_nodes_simulation.zip | Main server dashboard, MLX90640, camera, chainsaw detector | Best current RPi base.
RPi ZIP v3 | firenode_rpi_unified_system_v3_manual_start.zip | Earlier manual-start baseline | Reference only.
Zoom VTT/MP4 | /Users/.../ADM Lora Forest Fire/GMT20260331-121759_* | Client decisions and topology | Hybrid LoRa + Wi-Fi confirmed.
ESP32 PlatformIO firmware | /Users/.../ADM Fire/ESP/FireNode_ESP32_v5 | LoRa sender and ESP32 sensor base | Workspace artifact not originally named, but useful.

## Architecture
FireNode Architecture Summary
Implementation-ready decisions aligned to PDF, PNG, ZIP code, Zoom meeting, and latest clarifications.
Item | Decision | Reason / Acceptance Link | Status | Evidence | Date | Notes
Primary validated path | ESP32/RPi node sensors and RPi audio -> LoRa telemetry -> center/main RPi -> SQLite/API/dashboard/siren | Exercises fire, logging, packet delivery, dashboard, and event logging tests | Approved | PDF validation flow + client clarification | 2026-05-15 | Wi-Fi camera stream remains separate.
Field topology | Center/main RPi is also the backup/center node | User clarified physical placement | Approved | User answer #1 | 2026-05-15 | Center node owns MLX90640.
Remote node compute | Remote nodes are Raspberry Pi + ESP32 | RPi handles camera/audio; ESP32 handles sensor acquisition and LoRa | Approved | User answer #2 | 2026-05-15 | Avoid ESP32-only audio classification risk.
Camera coverage | All four nodes have daytime cameras; main dashboard views all feeds | User clarified final camera plan | Approved | User answer #4 | 2026-05-15 | Use fisheye or standard camera per budget/coverage.
Thermal coverage | One MLX90640 only, installed on center/main RPi | Latest instruction controls over earlier slide | Approved | User constraint | 2026-05-15 | Used primarily for night/thermal event view.
Power | 12V battery system for every node and main server | User clarified power source | Approved | User answer #5 | 2026-05-15 | Need buck converters and fusing.

## Phase Plan
Phase Plan
Build order from prototype to field-ready system.
Phase | Goal | Scope | Exit Criteria | Status | Owner | Dependencies | Notes
Phase 0 | Local repository + workbook baseline | Initialize local Git repo, create clean repo structure, commit workbook/code locally; push when remote is provided | Local repo, workbook, raspi baseline, ESP32 baseline, simulation docs | Done | Codex/User | GitHub repository available | Project snapshot pushed to GitHub; CI workflow retained locally until workflow scope is available.
Phase 1 | Working four-node dashboard prototype | Run RPi app on all nodes, show all daytime cameras, main thermal, existing chainsaw detector | All feeds and local node data visible on main dashboard | In Progress | Codex/User | Hardware and network access | Use existing v4 ZIP as base. ¦ Current focus: Hardware Bench Validation Phase (LoRa pair + serial gateway + packet ingest).
Phase 2 | LoRa telemetry integration | Add LoRa receiver service on main and node LoRa packet sender bridge | Sensor and alert packets arrive with RSSI/SNR and timestamps | Not Started | Codex/User | LoRa module wiring | Keep Wi-Fi for setup/video.
Phase 3 | Persistence and alerts | Readings DB, event DB, siren relay, alert acknowledgements | Fire/smoke/chainsaw events logged and siren triggers | Not Started | Codex | Phase 2 | Use SQLite first.
Phase 4 | Recording and dashboard polish | Record camera on chainsaw; all event clips indexed; UI health cards | Event replay from dashboard works | Not Started | Codex | Phase 1/3 | Use ffmpeg/OpenCV segment recording.
Phase 5 | Field validation | PDR/RSSI, alert latency, false alarm rate, battery runtime | PDR >70%, dashboard update <=1 min, tests documented | Not Started | User/Codex | Deployed hardware | Record all evidence here.
Phase 6 | AI upgrade path | Improve chainsaw detector and optional TFLite classifier | Measured precision/recall improves vs baseline | Not Started | Codex/User | Real audio dataset | Baseline remains rule/feature based.

## Detailed Steps
Detailed Steps
Implementation checklist. Update Status, Evidence, and Date Completed every time work is finished.
Step ID | Workstream | Task | Status | Owner | Depends On | Output | Evidence / Commit
S001 | Project Control | Create ADM FireNode workbook and update policy | Done | Codex | Reference workbook | Workbook created | This file
S002 | GitHub | Provide or create GitHub repository and branch | Done | User/Codex | None | Repo URL and branch | Pushed baseline to GitHub main
S003 | Repo | Import current RPi ZIP code into structured repo folders | Done | Codex | S002 local workaround | raspi/firenode-system | Local baseline created
S004 | Repo | Import ESP32 PlatformIO firmware as node firmware baseline | Done | Codex | S002 local workaround | firmware/esp32-firenode | Local baseline created
S005 | Backend | Add SQLite readings/events schema and migration scripts | Not Started | Codex | S003 | Migrations + storage module
S006 | LoRa | Build main RPi LoRa receiver service | Not Started | Codex/User | S003, LoRa wiring | lora_gateway.py
S007 | LoRa | Build node telemetry packet sender/bridge | Not Started | Codex/User | S004/S006 | Packet sender and ACK retry
S008 | Audio | Keep and improve RPi chainsaw detector | Not Started | Codex | S003 | Calibrated detector config and tests
S009 | Camera | Normalize all node daytime camera streams | Not Started | Codex/User | S003 | Camera grid stable on main dashboard
S010 | Thermal | Lock MLX90640 to main server only | Not Started | Codex | S003 | Thermal service and UI scope
S011 | Recording | Record detecting node camera when chainsaw event occurs | Not Started | Codex | S008/S009 | Event clips in media folder
S012 | Alerts | Add siren relay service and dashboard controls | Not Started | Codex/User | S005 | GPIO relay integration
S013 | Power | Add battery voltage telemetry and low-voltage warnings | Not Started | Codex/User | Hardware divider | battery_v in packets/readings
S014 | Testing | Create mocked integration tests for APIs, LoRa packets, and detector | Not Started | Codex | S005-S012 | pytest suite
S015 | Field | Run PDR/RSSI/latency/false alarm tests | Not Started | User/Codex | Hardware deployed | Test Campaign evidence
S016 | Deployment | Create automated Raspberry Pi deployment scripts using SSH key auth, simulation config, manual start default, and optional systemd service | Done | Codex | Hardware Bench Validation Phase / SSH key deployment complete | MacBook deployment scripts and beginner guide | bash -n passed for deployment scripts

## Hardware BOM
Hardware BOM
Bill of materials based on final clarified topology.
Category | Part | Qty | Unit Location | Purpose | Required / Optional | Notes | Risk
Compute | Raspberry Pi 4 preferred / Pi 3B+ minimum | 4 | All nodes | Camera, audio processing, local service | Required | Existing code targets RPi 3B but Pi 4 improves camera/audio reliability | Availability
Compute | ESP32 DevKit V1 | 4 | All nodes | Sensor acquisition and LoRa support | Required | Existing PlatformIO firmware base exists | GPIO/power noise
Radio | SX1278 / Ra-02 433 MHz LoRa module | 4 | Each node | LoRa telemetry | Required | Meeting said no strict module preference | Antenna tuning
Radio | LoRa receiver/gateway radio | 1 | Main RPi | Receive node packets | Required | Can be direct SPI to RPi or via gateway ESP32 serial bridge | Driver complexity
Camera | Daytime USB/CSI camera | 4 | All nodes | Live view and event recording | Required | Normal/daytime cameras on every node | Bandwidth
Thermal | MLX90640 | 1 | Main/center node only | Night/thermal event view | Required | Do not deploy on remote nodes | Cost/FOV
Sensor | DHT22 or Si7021 | 4 | All nodes | Temperature/humidity | Required | Si7021 preferred for stability | Calibration
Sensor | MQ2 smoke/gas sensor | 4 | All nodes | Smoke/fire indicator | Required | Add ADC/PPM if possible, not digital-only | Drift/heater power
Audio | USB mic or SPH0645 I2S MEMS mic | 4 | All nodes | Chainsaw detection | Required | RPi detector currently uses USB mic; I2S is cleaner later | False positives
Alert | 12V siren + LED beacon | 1 | Main/receiver or center node | Local alarm | Required | Drive through relay/MOSFET | Weatherproofing
Power | 12V battery system | 4 | All nodes | Field power | Required | User specified 12V 40A batteries | Runtime/charging
Power | 5V buck converter 5A+ | 4 | All nodes | RPi supply | Required | Use fused input and stable converter | Brownouts
Enclosure | Weatherproof box, glands, pole mount | 4 | All nodes | Field deployment | Required | Mount center node high enough for camera coverage | Water ingress

## Config Tracker
Config Tracker
Runtime configuration values to keep code, workbook, and field setup aligned.
Config Key | Recommended Value | Applies To | Source | Status | Notes
role | server for main, node for remotes | RPi app | Existing config.json | Approved | Main default in v4 ZIP is server.
port | 8090 | RPi app | Existing ZIP | Approved | Dashboard and node APIs.
server_refresh_sec | 3-5 | Main dashboard | Existing ZIP | Approved | UI can refresh faster than 1-minute telemetry.
telemetry_interval_sec | 60 | LoRa telemetry | PNG/PDF | Approved | Dashboard requirement says every 1 minute.
alert_retry_sec | 10 | LoRa alerts | Recommended | Proposed | Retry unacknowledged alert packets.
camera_fps | 8-10 | All RPi cameras | Existing ZIP | Approved | Lower if Wi-Fi bandwidth is weak.
thermal_refresh_rate_hz | 2 | Main thermal | Existing ZIP | Approved | MLX90640 over I2C.
sample_rate | 16000 | Chainsaw detector | Existing ZIP | Approved | Current detector.py default.
score_threshold | 60 | Chainsaw detector | Existing ZIP | Tune | Calibrate using field audio.
require_hits | 3 | Chainsaw detector | Existing ZIP | Tune | Multi-window confirmation.
battery_low_v | 11.4 | All nodes | Recommended | Proposed | Adjust to battery chemistry.
wifi_country | PH | All RPis/ESP32 | Existing config | Approved | Deployment in Philippines.
camera_backend | V4L2 | RPi USB cameras | Main server manual test | Implemented | Uses cv2.CAP_V4L2 on Linux/live mode.
camera_fourcc | MJPG | RPi USB cameras | Main server manual test | Implemented | Applied before width/height/fps.
camera_open_warmup_frames | 5 | RPi USB cameras | Main server manual test | Implemented | Discard initial frames after opening.
camera_retry_on_failed_read | true | RPi USB cameras | Main server issue | Implemented | Release/reopen capture after failed read.
camera_width | 320 | RPi USB cameras | Main server camera stability finding | Updated | Lower default for Raspberry Pi 3B USB stability.
camera_height | 240 | RPi USB cameras | Main server camera stability finding | Updated | Lower default for Raspberry Pi 3B USB stability.
camera_fps | 10 | RPi USB cameras | Main server camera stability finding | Updated | Reduced FPS to limit USB bandwidth/power stress.
camera_jpeg_quality | 55 | RPi USB cameras | Main server camera stability finding | Updated | Reduced JPEG quality for smaller MJPEG stream frames.
camera_fourcc | MJPG | RPi USB cameras | Main server camera stability finding | Updated | Keep MJPG as confirmed working format.
camera_open_warmup_frames | 10 | RPi USB cameras | Main server camera stability finding | Updated | Discard more startup frames before streaming.
camera_type | CSI (Raspberry Pi Camera Rev 1.3) | All RPis | Hardware decision 2026-06-02 | Approved | Replaces USB webcam.
camera_capture_module | rpicam/libcamera (planned) | All RPis | Implementation task P042 | Proposed | New module to replace OpenCV V4L2 path for production.
camera_sensor | ov5647 | All RPis | rpicam-hello --list-cameras | Confirmed | 2592x1944 10-bit GBRG.
camera_type | CSI (Raspberry Pi Camera Rev 1.3) | All RPis | Hardware decision 2026-06-02 | Approved | Replaces USB webcam.
camera_capture_module | Picamera2 (modules/csi_camera_stream.py) | All RPis | Implementation task P042 | Implemented | New module to replace OpenCV V4L2 path for production.
camera_sensor | ov5647 | All RPis | rpicam-hello --list-cameras | Confirmed | 2592x1944 10-bit GBRG.
camera_usb_fallback | True | All RPis | app.py DEFAULT_CONFIG | Approved | If Picamera2 fails, fall back to OpenCV USB camera path.
dashboard_mode | live | .51 MAIN | Field deployment 2026-06-08 | Approved | MAIN .51 runs in LIVE mode; simulation still available for local dev.
csi_camera_status_.51 | Pass | .51 MAIN | Hardware validation 2026-06-08 | Confirmed | CSI camera feed stable in LIVE mode.
csi_camera_status_.52 | Pass | .52 NODE_01 | Hardware validation 2026-06-08 | Confirmed | CSI camera feed visible on MAIN dashboard.
remote_aggregation_.52 | Pass | .51 MAIN | Integration validation 2026-06-08 | Confirmed | MAIN discovers/pulls NODE_01 data and camera.
esp32_serial_status | Implemented / Pending Verification | .51 MAIN | Serial integration 2026-06-08 | In Progress | Code complete; minicom confirmed hardware; dashboard overlay pending live validation.
node_02_03_build_status | Pending | .53/.54 | Hardware build 2026-06-08 | Not Started | CSI cameras installed; ESP32 + LoRa + sensors not assembled.
thermal_camera_status | Pending Installation | .51 MAIN | Design retention 2026-06-08 | Approved | Retained as MAIN-only design component; not physically installed yet.
chainsaw_detection_status | Pending USB Microphone | All nodes | Audio pipeline 2026-06-08 | Not Started | detector.py ready; USB microphone installation and live testing pending.

## Packet Protocol
Packet Protocol
LoRa telemetry and alert payloads.
Field | Type | Required | Example | Producer | Consumer | Notes
v | int | Yes | 1 | Node | Main | Protocol version.
node_id | string | Yes | node-02 | Node | Main | Stable ID, not only IP.
seq | int | Yes | 1842 | Node | Main | Used for packet loss/PDR.
ts | unix/int | Preferred | 1778640000 | Node | Main | Gateway can timestamp if node clock unavailable.
temp_c | float | Yes | 34.2 | ESP32/RPi | Main | DHT22/Si7021.
humidity | float | Yes | 58.1 | ESP32/RPi | Main | Relative humidity %.
smoke_ppm | float | Preferred | 420 | ESP32 | Main | Use analog MQ2 when possible.
smoke_detected | bool | Yes | false | ESP32 | Main | Digital fallback.
chainsaw_score | float | Yes | 72 | RPi | Main | From detector.py.
chainsaw_detected | bool | Yes | true | RPi | Main | Triggers recording.
battery_v | float | Yes | 12.4 | ESP32/RPi | Main | Voltage divider.
events | array | Yes | ["CHAINSAW"] | Node | Main | Compact event list.
rssi | float | Gateway | -91 | LoRa receiver | DB/dashboard | Measured at gateway.
snr | float | Gateway | 7.5 | LoRa receiver | DB/dashboard | Measured at gateway.
Example JSON
{"v":1,"node_id":"node-02","seq":1842,"temp_c":34.2,"humidity":58.1,"smoke_ppm":420,"chainsaw_score":72,"chainsaw_detected":true,"battery_v":12.4,"events":["CHAINSAW"]}

## Backend APIs
Backend APIs
Flask-compatible API plan extending the current RPi ZIP.
Endpoint | Method | Owner Service | Purpose | Payload / Response | Status | Notes
/ | GET | dashboard | Web dashboard | HTML | Existing | Keep current dashboard route.
/api/status | GET | dashboard_api | Server, thermal, LoRa, DB, battery health | JSON | Existing/Extend | Add LoRa and DB status.
/api/node-data | GET | node_api | Local node snapshot | JSON | Existing/Extend | Keep backward compatibility.
/api/server-dashboard | GET | dashboard_api | Aggregate all node status | JSON | Existing/Extend | Use DB + live health.
/api/nodes | GET | node_registry | List configured nodes | JSON | New | Stable node IDs.
/api/readings | GET | sensor_store | Historical readings | JSON | New | Filter by node/time.
/api/events | GET | event_store | Alert/event list | JSON | New | Media path included.
/api/events/{id}/ack | POST | event_store | Acknowledge event | JSON | New | Audit user/time.
/api/stream | GET | dashboard_api | SSE live updates | text/event-stream | New | Better than page polling.
/video_feed/<node_id> | GET | camera_proxy | View camera stream | MJPEG | Extend | Proxy local/remote feeds.
/thermal_feed | GET | thermal_service | Main MLX90640 stream | MJPEG/PNG | Existing | Main server only.
/api/siren | POST | siren_service | Trigger/test/disable alarm | JSON | New | Protect with auth.

## Database Schema
Database Schema
SQLite-first schema for readings, events, media, nodes, and checks.
Table | Key Fields | Purpose | Indexes | Retention | Status | Notes
nodes | id, name, role, ip, has_camera, has_thermal, last_seen | Inventory and online state | PRIMARY KEY(id) | Permanent | New | Main node has has_thermal=1.
readings | id, node_id, ts, temp_c, humidity, smoke_ppm, chainsaw_score, battery_v, rssi, snr | 1-minute telemetry and health | node_id, ts | 30-90 days | New | Use for charts and validation.
events | id, node_id, ts, type, severity, message, evidence_json, media_path, acked | Alert/event log | type, ts, node_id | Permanent | New | Replaces alert-only DB.
media | id, event_id, node_id, path, camera_id, start_ts, duration_sec | Recorded video metadata | event_id | Rotate by storage | New | Clip files on disk.
lora_packets | id, node_id, seq, rx_ts, rssi, snr, payload_json, accepted | PDR/RSSI audit | node_id, seq | 30-90 days | New | Supports PDF performance metrics.
settings_history | id, ts, key, old_value, new_value, actor | Config change audit | ts | Permanent | Optional | Useful for field tuning.

## Dashboard UX
Dashboard UX
Main web dashboard behavior.
View | Components | Data Source | Update Method | Acceptance | Status | Notes
Overview | 4 node cards, alarm state, battery, LoRa PDR/RSSI, latest readings | /api/server-dashboard + /api/stream | SSE + fallback polling | All nodes visible within one screen | Extend | Keep utilitarian dashboard style.
Camera Grid | 4 daytime camera feeds | /video_feed/<node_id> | MJPEG | All feeds viewable from main server | Extend | Use low FPS/resolution if Wi-Fi weak.
Thermal | Main MLX90640 heat map and detection metrics | /thermal_feed | MJPEG/PNG | Only main server thermal appears | Existing/Constrain | No remote thermal panels.
Alerts | Active alerts, ack button, siren state | /api/events | SSE/poll | Smoke/chainsaw/fire events prominent | New | Record audit trail.
History | Reading charts, event clips, logs | /api/readings /api/events | On demand | Filter by node/date/event | New | Useful for thesis validation.
Settings | Node IPs, LoRa, thresholds, camera, audio, siren, Wi-Fi | /api/config | Manual save | Changes logged | Extend | Avoid web-triggered Wi-Fi changes that disconnect RPi.

## AI & Detection
AI & Detection
Baseline and upgrade path for fire, chainsaw, and thermal detection.
Detection | Baseline Logic | Current Code / Source | Improvement | Metrics | Status | Notes
Fire Risk | Temp >= threshold AND humidity <= threshold | PDF algorithm | Add site-calibrated thresholds and trend filter | Warning latency, false warnings/day | Proposed | Warning only until smoke confirms.
Fire Alert | Fire risk AND smoke above threshold/detected | PDF algorithm | Use analog PPM plus digital fallback | Recall, alert latency | Proposed | Triggers siren.
Chainsaw | RPi FFT/RMS/mechanical-band score with multi-window confirmation | detector.py in RPi ZIPs | Noise floor tracking, calibration, persistence, optional TFLite classifier | Precision, recall, false positives/hour | Existing/Improve | Do not move primary detector to ESP32.
Thermal Event | MLX90640 blob temp >= ambient + delta, min area, persistence | thermal_camera.py | Add night-mode thresholds and false hot-spot suppression | Detection latency, false positives | Existing/Main only | Only center/main node.
Camera Smoke/Flame | None in baseline | N/A | Optional YOLO/TFLite only after dataset exists | Precision/recall/FPS | Future | Not required for initial build.

## Camera & Recording
Camera & Recording
Daytime camera feeds on all nodes and main thermal behavior.
Feature | Design | Trigger | Storage / URL | Status | Notes
Daytime camera | One normal camera per node including main | Always available while app running | /video_feed/<node_id> | Approved | All feeds viewable on main dashboard.
Thermal camera | One MLX90640 on center/main RPi | Night mode/manual/dashboard | /thermal_feed | Approved | No remote thermal camera.
Chainsaw recording | Record detecting node's daytime camera; optionally record main camera too | chainsaw_detected true | media/YYYY-MM-DD/<event_id>_<node_id>.mp4 | New | Use pre-roll buffer if feasible.
Smoke/fire evidence | Snapshot/short clip from node camera | fire alert/smoke alert | media/YYYY-MM-DD/<event_id>_<node_id>.jpg/mp4 | New | Useful for validation.
Retention | Rotate clips by age/storage | Scheduled cleanup | configurable | New | Do not fill SD card.
USB camera capture format | Live mode opens /dev/videoN with V4L2, applies MJPG FOURCC before size/FPS, discards warmup frames, and reopens on read failure | RPi dashboard live camera | /video_feed and /video_feed/<index> | Implemented; pending RPi validation | Does not affect thermal stream or simulation mode.
RPi 3B camera stability defaults | Use 320x240, 10 FPS, JPEG quality 55, MJPG, 10 warmup frames before trying higher settings | Live USB camera | /video_feed and camera_test.py | Updated; pending RPi validation | Corrupt MJPG frames can indicate USB bandwidth or camera power limits.

## Deployment DevOps
Deployment DevOps
Run, recover, monitor, and update the field system.
Area | Recommendation | Applies To | Status | Command / Config | Notes
Process manager | systemd services for RPi app, LoRa gateway, recording worker | All RPis | Proposed | firenode-app.service | Restart=always.
Runtime | Python venv with system-site packages on RPi OS | All RPis | Existing | setup.sh | Matches current ZIP.
Firmware build | PlatformIO for ESP32 | ESP32 nodes | Existing | pio run / upload | Add CI build later.
Config | config.json plus environment override | All RPis | Existing/Extend | config.json | Track changes in workbook.
Logging | Rotating logs + SQLite events | All RPis/main | New | logs/*.log, logs/fire_node.db | Avoid SD card growth.
CI | Python tests + PlatformIO build + workbook committed | GitHub | Partial | GitHub Actions | Workflow file exists locally but HTTPS token lacks workflow scope; pushed baseline without workflow.
Deployment | Tagged releases or zip package per node role | GitHub | Future | release artifacts | Keep main/node config examples.
Automated RPi deployment | Use MacBook scripts to rsync app files, run setup, create venv, install requirements, write config, and create optional systemd service | All four RPis | Implemented | ./scripts/deploy_all_rpis.sh | Uses ~/admfire key, user betech, simulation mode, manual start default
Manual start deployment mode | Default behavior leaves service disabled; operator starts ./run.sh manually or enables service later | All four RPis | Implemented | ./scripts/deploy_node.sh --install-service optional | Avoids surprise autostart during first hardware bench setup

## Test Campaign
Test Campaign
Validation plan tied to PDF and field demo requirements.
Test ID | Test | Procedure | Expected Result | Metric | Status | Evidence
T001 | Dashboard 1-minute update | Run all nodes and observe sensor updates | Temp/humidity/smoke/audio status update within 60 sec | Update latency | Not Started
T002 | Smoke introduction | Introduce safe smoke source near MQ2 | Fire alert + siren activation | Detection latency | Not Started
T003 | Fire risk warning | Simulate high temp and low humidity without smoke | Warning state, no siren | False alarm prevention | Not Started
T004 | Chainsaw audio | Play chainsaw/chopping audio near node | Chainsaw alert and camera recording | Score, latency, clip path | Not Started
T005 | Thermal night/main only | Place warm human-like target near main MLX90640 | Thermal event on main only | Thermal score | Not Started
T006 | Camera grid | Open main dashboard | All 4 daytime feeds visible | FPS/stability | Not Started
T007 | LoRa PDR | Send 100 telemetry packets per node | PDR >70% | PDR/RSSI/SNR | In Progress | MAIN↔NODE_01 2-way PASS; NODE_02/NODE_03 pending hardware
T008 | Offline node | Power off one node | Dashboard marks offline after missed heartbeats | Offline latency | Not Started
T009 | Battery warning | Inject/measure low battery voltage | Low-voltage warning logged | Voltage accuracy | Not Started
T010 | Siren control | Trigger alert and manual test | Relay/siren operates, cooldown works | Activation time | Not Started
T011 | CSI camera detection | Run rpicam-hello --list-cameras on each RPi | ov5647 sensor appears with supported modes | Sensor presence | Done | .51/.52/.53/.54 confirmed
T012 | CSI still capture | Run rpicam-still -o /tmp/csi_test.jpg on each RPi | JPEG saved without corruption | Image clarity | Not Started | Pending pipeline integration
T013 | CSI MJPEG stream | Open /video_feed after app integration | MJPEG stream returns clear frames at configured resolution/FPS | Stream stability | Not Started | Pending P042
T011 | CSI camera detection | Run rpicam-hello --list-cameras on each RPi | ov5647 sensor appears with supported modes | Sensor presence | Done | .51/.52/.53/.54 confirmed
T012 | CSI still capture | Run rpicam-still -o /tmp/csi_test.jpg on each RPi | JPEG saved without corruption | Image clarity | Done | rpicam-still confirmed on .51/.52/.53/.54
T013 | CSI MJPEG stream | Open /video_feed after app integration | MJPEG stream returns clear frames at configured resolution/FPS | Stream stability | Done | modules implemented and deployed to .51/.52/.53/.54; /video_feed validated
T022 | CSI camera validation .51 | Open MAIN dashboard in LIVE mode and verify local camera feed | Clear MJPEG stream from .51 CSI camera at configured resolution/FPS | Stream stability | Done | Visual inspection; rpicam-hello confirmed ov5647 on .51
T023 | CSI camera validation .52 | Open MAIN dashboard remote camera grid and verify NODE_01 feed | Clear MJPEG stream from .52 CSI camera visible on MAIN dashboard | Stream stability | Done | Visual inspection; rpicam-hello confirmed ov5647 on .52
T024 | Remote node aggregation .51 to .52 | Observe MAIN dashboard sensor cards and node inventory | Remote slot 1 shows NODE_01 sensor data and camera; node marked online | Data latency / accuracy | Done | Dashboard JSON shows remote slot 1 populated; network reachability confirmed
T025 | MAIN ESP32 USB serial reader implementation | Review code, run py_compile, and inspect config | modules/esp32_serial_reader.py compiles; config keys present; thread-safe cache logic correct | Code quality | Done | python3 -m py_compile passed; unit parse test passed
T026 | MAIN ESP32 serial hardware confirmation | Run minicom on /dev/ttyUSB0 at 115200 and observe packets | NODE=MAIN and NODE=NODE_01 packets readable; no garbled output | Serial integrity | Done | Minicom session recorded packet examples at 115200
T027 | MAIN ESP32 dashboard live sensor integration | Deploy code to .51 MAIN and observe sensor cards | Local node card shows TEMP/HUM/PIR/MQ/BAT from serial cache; serial_connected=true | Integration accuracy | In Progress | Code implemented; pending .51 availability for deployment and live validation. DO NOT MARK PASS YET.
T028 | .53/.54 hardware build readiness | Physical inspection of NODE_02/NODE_03 assemblies | ESP32 + LoRa + sensors + CSI camera wired and powered | Hardware completeness | In Progress | CSI cameras installed and validated on .53/.54; ESP32 + LoRa + sensors pending assembly.
T029 | Thermal camera installation readiness | Inspect MAIN RPi for MLX90640 I2C connection | Thermal camera mounted and /thermal_feed returns frames | Hardware completeness | Not Started | Module exists in code; hardware not installed.
T030 | Chainsaw detection readiness | Install USB microphone and run detector.py with test audio | detector.py detects chainsaw-like audio and triggers alert + recording | Detection latency / accuracy | Not Started | Synthetic test audio exists; live microphone pending.
T031 | CSI camera validation .53 | Open NODE_02 dashboard in LIVE mode and verify local camera feed | Clear MJPEG stream from .53 CSI camera at configured resolution/FPS | Stream stability | Done | Visual inspection; rpicam-hello confirmed ov5647 on .53; required python3-picamera2 and file sync
T032 | CSI camera validation .54 | Open NODE_03 dashboard in LIVE mode and verify local camera feed | Clear MJPEG stream from .54 CSI camera at configured resolution/FPS | Stream stability | Done | Visual inspection; rpicam-hello confirmed ov5647 on .54; required python3-picamera2 and sync of modules/multi_camera_stream.py
T033 | python3-picamera2 dependency check | Run dpkg -s python3-picamera2 on .53 and .54 | Package is installed | Dependency presence | Done | sudo apt install -y python3-picamera2 executed on .53/.54
T034 | Deployment sync checklist .53/.54 | Verify app.py, static/app.js, templates/dashboard.html, modules/csi_camera_stream.py, modules/multi_camera_stream.py, config.json, .deployment.env | Files synced and node-specific configs correct | Deployment accuracy | Done | NODE_02 required all listed files; NODE_03 required app.py, static/app.js, modules/csi_camera_stream.py, modules/multi_camera_stream.py, config

## Progress Tracker
Progress Tracker
One row per completed or pending implementation step.
Step ID | Workstream | Task | Status | Owner | Date Completed | Evidence | Next Action
P001 | Research | Inspected PDF, PNG, ZIPs, Zoom transcript/video, and ESP32 firmware context | Done | Codex | 2026-05-15 | Chat analysis and artifacts | Use workbook as source of truth
P002 | Architecture | Resolved final topology: 4 RPi field units, hybrid LoRa/Wi-Fi, one thermal on main | Done | Codex/User | 2026-05-15 | User clarification answers | Implement repo baseline
P003 | Workbook | Create implementation workbook similar to MANET reference | Done | Codex | 2026-05-15 | ADM_FireNode_Implementation_Workbook.xlsx | Commit workbook to GitHub
P004 | Git | Initialize local Git repository and clean ignore rules | Done | Codex | 2026-05-15 | git init; .gitignore | Provide GitHub remote URL for push
P005 | Code Baseline | Unpack and structure RPi and ESP32 code into repo | Done | Codex | 2026-05-15 | raspi/firenode-system; firmware/esp32-firenode | Run simulation baseline
P006 | Simulation | Add simulation run documentation and start script | Done | Codex | 2026-05-15 | simulation/README.md; scripts/start_main_simulation.sh | Run script in compatible Python/RPi environment
P010 | Simulation | Boot main dashboard in simulation mode and verify API node inventory | Done | Codex | 2026-05-15 | HTTP 200 on /; /api/server-dashboard shows 4 nodes and 3 simulated remotes | Add cv2-free simulated local camera fallback
P011 | Simulation | Add cv2-free local main camera fallback and verify main camera stream | Done | Codex | 2026-05-15 | /api/server-dashboard local camera running=true simulation=true; /video_feed/0 returns MJPEG | Implement LoRa packet simulation/receiver path
P012 | LoRa Simulation | Add simulated LoRa packet receiver contract with seq/RSSI/SNR/PDR/battery fields | Done | Codex | 2026-05-15 | /api/lora/status shows 4 active nodes and packet history; dashboard node JSON includes lora object | Implement real LoRa receiver adapter and SQLite packet store
P013 | LoRa Storage | Add SQLite LoRa packet store and packet ingest/history APIs | Done | Codex | 2026-05-15 | /api/lora/packets returns stored packet rows; /api/lora/ingest accepts future gateway packets | Implement real LoRa receiver adapter
P014 | LoRa Gateway | Add serial gateway adapter that reads one JSON packet per line and posts to /api/lora/ingest | Done | Codex | 2026-05-15 | lora_gateway_serial.py compiles; pyserial added to requirements | Build ESP32 gateway firmware packet output
P015 | Firmware | Add ESP32 LoRa gateway firmware that receives SX1278 packets and prints JSON lines for the Pi adapter | Done | Codex | 2026-05-15 | firmware/esp32-lora-gateway; parser smoke test ignores gateway status and accepts packets | Add automated tests for LoRa parser/store APIs
P016 | Tests | Add automated LoRa parser/store/simulator tests and runner | Done | Codex | 2026-05-15 | ./scripts/run_raspi_tests.sh ran 4 tests OK | Implement camera recording on chainsaw event
P017 | Recording | Add chainsaw event snapshot recorder and recordings API | Done | Codex | 2026-05-15 | ./scripts/run_raspi_tests.sh ran 5 tests OK; /api/recordings added | Add dashboard recording list
P018 | Dashboard | Add recent recordings panel to dashboard and serve recording snapshots through /media | Done | Codex | 2026-05-15 | / returned 200; /api/recordings returned JSON; tests passed | Add CI workflow
P019 | CI/CD | Add GitHub Actions workflow for Raspberry Pi app tests and ESP32 firmware builds | Done | Codex | 2026-05-15 | .github/workflows/ci.yml; local Python tests passed; PlatformIO not installed locally | Add deployment/systemd scripts
P020 | Deployment | Add systemd install/stop scripts for LoRa serial gateway bridge | Done | Codex | 2026-05-15 | bash -n service scripts; README updated | Add API smoke-test script
P021 | Testing | Add simulation smoke test that boots dashboard and verifies APIs | Done | Codex | 2026-05-15 | ./scripts/smoke_test_main_simulation.py passed; added to CI | Add field deployment checklist/docs
P022 | Deployment | Add field deployment checklist for bench, main node, remote nodes, LoRa, cameras, alerts, shutdown | Done | Codex | 2026-05-15 | docs/deployment/field_deployment_checklist.md | Add hardware wiring reference
P023 | Hardware | Add wiring reference aligned to ESP32 sender and gateway firmware defaults | Done | Codex | 2026-05-15 | docs/hardware/wiring_reference.md | Add README links to new docs
P024 | Documentation | Update top-level README with fast start and links to workbook, simulation, deployment, hardware, firmware docs | Done | Codex | 2026-05-15 | README.md | Add release/package script
P025 | Release | Add Git archive release packaging script | Done | Codex | 2026-05-15 | ./scripts/package_release.sh created dist/adm-firenode-b658810-20260514-140648.zip | Add packet schema documentation
P026 | Documentation | Add LoRa packet and API schema contract | Done | Codex | 2026-05-15 | docs/api/lora_packet_schema.md; README.md | Run full local verification and prepare GitHub push when remote is available
P027 | Verification | Run full local verification after simulation/LoRa/recording/docs work | Done | Codex | 2026-05-15 | Unit tests OK; smoke test OK; compileall OK; release zip created; git clean | Push to GitHub
P028 | AI Workflow | Add hybrid low-cost AI workflow memory sheets to workbook | Done | Codex | 2026-05-15 | AI Stack; AI Router; Active Context Snapshot; Handoff; Prompt Library; Validation Matrix; Logs | Use workbook + GitHub as persistent memory
P007 | GitHub | Create/provide GitHub repo and branch and push project snapshot | Done | User/Codex | 2026-05-15 | https://github.com/pagibetech/adm-firenode-forest-monitoring commit 05e1a77 | Enable workflow scope later to push CI file
P008 | LoRa Gateway | Add main RPi LoRa receiver service | Done | Codex/User | 2026-05-15 | Superseded by P014 (serial gateway) and P015 (gateway firmware) | Use simulator packet contract as receiver API target
P009 | Recording | Add camera recording on chainsaw detection | Done | Codex | 2026-05-15 | Superseded by P017 (event recorder) and P018 (dashboard panel) | Implement after simulation camera feeds are stable
P029 | Deployment | Created MacBook-run automated Raspberry Pi deployment scripts for main server and three nodes in simulation mode | Done | Codex | 2026-05-20 | scripts/deploy_main_server.sh; scripts/deploy_node.sh; scripts/deploy_all_rpis.sh; docs/deployment/rpi_automated_deployment.md | Run ./scripts/deploy_all_rpis.sh from MacBook when RPis are reachable
P030 | Deployment | Updated Raspberry Pi deployment scripts for parallel default, sequential mode, single-target deploy, per-IP logs, final pass/fail summary, and deployment role labels | Done | Codex | 2026-05-20 | bash -n passed; deploy_all help checked; Python tests and smoke test passed | Run ./scripts/deploy_all_rpis.sh from MacBook
P031 | Camera | Added configurable USB camera capture format for Raspberry Pi live mode after /dev/video0 required V4L2 + MJPG to read frames | Done; pending RPi redeploy validation | Codex | 2026-05-21 | camera_stream.py; camera_test.py; config fields; docs/workbook/status updates | ./scripts/deploy_all_rpis.sh --target 192.168.9.51 --skip-setup
P032 | Camera | Lowered Raspberry Pi 3B USB camera defaults after corrupted MJPG frames at higher settings | Done; pending RPi validation | Codex | 2026-05-21 | app/config/static/deploy/docs/workbook updated | ./scripts/deploy_all_rpis.sh --target 192.168.9.51 --skip-setup
P033 | Hardware | ESP32 MAIN + NODE_01 bench validation | Done | User/Codex | 2026-06-02 | DHT22/PIR/MQ/LoRa TX/RX validated on MAIN and NODE_01 | Continue ESP32-to-RPi integration
P034 | Hardware | LoRa two-way MAIN ↔ NODE_01 communication validation | Done | User/Codex | 2026-06-02 | RSSI -29 to -35 dBm; SNR 9.25 to 10.00 | Integrate LoRa packet ingest into RPi dashboard/API
P035 | Hardware | USB webcam compatibility assessment on RPi 3B | Done; Blocked | User/Codex | 2026-06-02 | YUYV fails; MJPG works but distorted/corrupted | Replace camera or use powered USB hub before field deployment
P036 | Hardware | Battery ADC check on MAIN ESP32 | Done; Issue found | User/Codex | 2026-06-02 | Battery ADC appears floating/unconnected | Verify voltage divider wiring and ADC pin assignment
P037 | Hardware | Raspberry Pi Camera Rev 1.3 CSI selected as official camera hardware; USB webcam deprecated | Done | User/Codex | 2026-06-02 | ov5647 detected on .51/.52; rpicam-hello --list-cameras confirmed | Implement rpicam/libcamera capture pipeline in RPi app
P038 | Hardware | .51 MAIN CSI camera detection confirmed (ov5647 [2592x1944 10-bit GBRG]) | Done | User | 2026-06-02 | rpicam-hello --list-cameras output recorded | Validate still capture and integrate into app
P039 | Hardware | .52 NODE_01 CSI camera detection confirmed (ov5647 [2592x1944 10-bit GBRG]) | Done | User | 2026-06-02 | rpicam-hello --list-cameras output recorded | Validate still capture and integrate into app
P040 | Hardware | .53 NODE_02 Raspberry Pi Camera Rev 1.3 CSI installed; pending physical confirmation | Done | User | 2026-06-02 | rpicam-hello confirmed ov5647 on .53; python3-picamera2 installed; file sync completed; local dashboard stream validated. | ESP32 hardware assembly for NODE_02
P041 | Hardware | .54 NODE_03 Raspberry Pi Camera Rev 1.3 CSI installed; pending physical confirmation | Done | User | 2026-06-02 | rpicam-hello confirmed ov5647 on .54; python3-picamera2 installed; modules/multi_camera_stream.py synced from NODE_01; local dashboard stream validated. | ESP32 hardware assembly for NODE_03
P042 | Camera | Implement Raspberry Pi CSI camera pipeline using rpicam/libcamera | Not Started | Codex/User |  | Replace USB/OpenCV capture path; keep simulation fallback | Deploy to .51/.52 and validate /video_feed endpoint
P037 | Hardware | Raspberry Pi Camera Rev 1.3 CSI selected as official camera hardware; USB webcam deprecated | Done | User/Codex | 2026-06-02 | ov5647 detected on .51/.52; rpicam-hello --list-cameras confirmed | Implement rpicam/libcamera capture pipeline in RPi app
P038 | Hardware | .51 MAIN CSI camera detection confirmed (ov5647 [2592x1944 10-bit GBRG]) | Done | User | 2026-06-02 | rpicam-hello --list-cameras output recorded | Validate still capture and integrate into app
P039 | Hardware | .52 NODE_01 CSI camera detection confirmed (ov5647 [2592x1944 10-bit GBRG]) | Done | User | 2026-06-02 | rpicam-hello --list-cameras output recorded | Validate still capture and integrate into app
P040 | Hardware | .53 NODE_02 Raspberry Pi Camera Rev 1.3 CSI installed; pending physical confirmation | Done | User | 2026-06-02 | rpicam-hello confirmed ov5647 on .53; python3-picamera2 installed; file sync completed; local dashboard stream validated. | ESP32 hardware assembly for NODE_02
P041 | Hardware | .54 NODE_03 Raspberry Pi Camera Rev 1.3 CSI installed; pending physical confirmation | Done | User | 2026-06-02 | rpicam-hello confirmed ov5647 on .54; python3-picamera2 installed; modules/multi_camera_stream.py synced from NODE_01; local dashboard stream validated. | ESP32 hardware assembly for NODE_03
P042 | Camera | Implement Raspberry Pi CSI camera pipeline using Picamera2 | Done | Codex/User | 2026-06-09 | modules/csi_camera_stream.py created; multi_camera_stream.py updated; app.py/config updated; py_compile passed; deployed and validated on .51/.52/.53/.54 | Verify MAIN ESP32 serial integration when .51 is reachable
P054 | Hardware | CSI camera validation .51 PASS | Done | User/Codex | 2026-06-08 | MAIN .51 dashboard in LIVE mode; CSI camera feed confirmed | Validate .52 NODE_01 camera feed on MAIN dashboard
P055 | Hardware | CSI camera validation .52 PASS | Done | User/Codex | 2026-06-08 | NODE_01 .52 CSI camera works and appears on MAIN dashboard | Validate remote node aggregation from .52 to .51
P056 | Integration | Remote node aggregation .51 to .52 PASS | Done | User/Codex | 2026-06-08 | MAIN can discover/pull NODE_01 data; remote slot 1 populated | Validate ESP32 serial reader deployment on .51
P057 | Integration | MAIN ESP32 USB serial reader IMPLEMENTED / PENDING VERIFICATION | In Progress | Codex | 2026-06-08 | modules/esp32_serial_reader.py created; app.py/config updated; py_compile passed; manual Minicom confirmed /dev/ttyUSB0 at 115200 | Deploy to .51 MAIN and validate live serial sensor cards
P058 | Hardware | MAIN ESP32 serial hardware manually confirmed using Minicom | Done | User | 2026-06-08 | Serial packet examples: NODE=MAIN,SEQ=1765,TEMP=27.70,HUM=62.90,PIR=0,MQ=356,BAT=0; NODE=NODE_01,SEQ=1765,TEMP=27.20,HUM=63.20,PIR=0,MQ=2095,BAT=2926 | Deploy serial reader code and confirm dashboard integration
P059 | Hardware | .53 NODE_02 and .54 NODE_03 pending hardware build | In Progress | User | 2026-06-08 | CSI cameras installed and validated on .53/.54; ESP32 hardware not yet assembled; no power/LoRa validation possible | Assemble NODE_02/NODE_03 ESP32 + LoRa + sensor wiring and validate with NODE_01 baseline
P060 | Hardware | Thermal camera pending installation, but retained as MAIN-only design component | Not Started | User/Codex | 2026-06-08 | MLX90640 is in BOM and design; not physically installed on MAIN yet | Install thermal camera on MAIN and validate /thermal_feed endpoint
P061 | Audio | Chainsaw detection pending USB microphone installation/testing | Not Started | User/Codex | 2026-06-08 | detector.py baseline exists; no USB microphone connected to any node for live validation | Install USB microphone on a node, run detector.py, and validate chainsaw alert + recording
P062 | Hardware | CSI camera validation .53 PASS | Done | User/Codex | 2026-06-09 | NODE_02 .53 dashboard in LIVE mode; CSI camera feed clear and stable; python3-picamera2 installed | Validate ESP32 hardware assembly for NODE_02
P063 | Hardware | CSI camera validation .54 PASS | Done | User/Codex | 2026-06-09 | NODE_03 .54 dashboard in LIVE mode; CSI camera feed clear and stable; python3-picamera2 installed; modules/multi_camera_stream.py synced from NODE_01 | Validate ESP32 hardware assembly for NODE_03
P064 | Integration | MAIN ESP32 USB serial reader PENDING VERIFICATION (blocked by .51 unavailability) | In Progress | Codex | 2026-06-09 | modules/esp32_serial_reader.py created; app.py/config updated; py_compile passed; manual Minicom confirmed /dev/ttyUSB0 at 115200; .51 unreachable for live validation | Deploy to .51 MAIN and validate live sensor cards from serial cache when .51 is reachable
P046 | Frontend | Create separate one-page web GUI for NODE RPis only | Done | Codex | 2026-06-09 | node_dashboard.html and node_app.js created; app.py routes node role to node_dashboard.html | Deploy to .52/.53/.54 and verify NODE GUI loads correctly
P047 | Frontend | Move chainsaw controls to NODE dashboard page | Done | Codex | 2026-06-09 | Chainsaw start/stop, sensitivity settings, audio test browser in node_dashboard.html | Deploy and verify chainsaw detection from NODE GUI
P048 | Frontend | Disable simulation mode for NODE RPis | Done | Codex | 2026-06-09 | operation_mode() forced to live when current_role() == node; simulation UI removed from NODE GUI | Deploy and verify NODE-only live mode on .52/.53/.54

## Issue Log
Issue Log
Risks, blockers, defects, and open questions.
Issue ID | Type | Description | Impact | Owner | Status | Resolution / Next Step
I001 | GitHub Blocker | Local Git repo existed without target remote/branch | Cannot push workbook/code to GitHub yet | User/Codex | Resolved | GitHub repo created and baseline pushed to main at commit 05e1a77.
I007 | GitHub Workflow Scope | HTTPS credential can push code but cannot create/update .github/workflows/ci.yml without workflow scope | CI workflow is preserved locally but not yet on GitHub | User/Codex | Open | Enable workflow scope or install GitHub app permissions, then push .github/workflows/ci.yml.
I002 | Architecture Conflict | Older diagram/meeting slide listed 4 thermal cameras, but latest instruction says only one thermal camera on main | Could cause BOM/design mismatch | Codex | Resolved | Workbook uses latest instruction as controlling requirement.
I003 | Protocol Gap | Current RPi ZIPs poll ESP32 over Wi-Fi and do not implement real LoRa gateway receive path | LoRa validation cannot pass yet | Codex | Open | Add LoRa receiver and packet store.
I004 | Power Detail | 12V 40A was specified, but battery chemistry/capacity in Ah not confirmed | Runtime and low-voltage thresholds uncertain | User | Open | Confirm battery chemistry and Ah rating.
I005 | Field Audio | No real chainsaw/forest dataset confirmed | ML classifier cannot be validated yet | User/Codex | Open | Start with existing detector and collect field clips.
I006 | Simulation Gap | Local main camera reported cv2 missing in the macOS venv while remote node camera simulation worked | Camera-grid test was not complete until local fallback feed worked without hardware | Codex | Resolved | Added PIL-based local camera fallback for simulation mode; live mode still uses OpenCV on Raspberry Pi.
I008 | ESP32/SX1278 Hardware Validation Paused | ESP32 firmware builds/uploads, but real SX1278/Ra-02 validation is paused due to likely wiring or power instability | Do not modify ESP32 firmware or start real LoRa integration during RPi simulation deployment phase | User/Codex | Resolved | ESP32 MAIN + NODE_01 bench validation PASSED. LoRa two-way confirmed. Resume integration work.
I009 | Main Server USB Camera Frame Read Failed | Main server dashboard/API work on 192.168.9.51, but /dev/video0 live camera reads failed with default OpenCV capture | Dashboard camera panel unavailable until capture uses V4L2 + MJPG settings | User/Codex | Mitigated in code; pending RPi validation | Added configurable camera_backend, camera_fourcc, warmup frames, retry/reopen, and camera_test.py.
I010 | RPi 3B USB Camera Corrupt MJPG Frames | USB stream works but image is corrupted/unclear; manual MJPG test warned Corrupt JPEG data: premature end of data segment | Dashboard image quality unstable at higher USB camera settings | User/Codex | Hardware blocker identified | Lowered defaults to 320x240, 10 FPS, JPEG quality 55, MJPG, 10 warmup frames. USB webcam still produces distorted/corrupted MJPG on RPi 3B. Recommend camera replacement or powered USB hub.
I011 | Hardware | Battery ADC on MAIN appears floating/unconnected | Battery telemetry unavailable on MAIN | User/Codex | Open | Verify voltage divider wiring and ADC pin assignment on MAIN ESP32.
I012 | Hardware | USB webcam compatibility blocker on RPi 3B | Daytime camera feeds may be unavailable or corrupted in field | User/Codex | Open | Resolved | USB webcam deprecated. Replaced with Raspberry Pi Camera Rev 1.3 CSI.
I013 | Hardware | NODE_02 and NODE_03 ESP32 hardware not yet assembled | Cannot validate full 4-node LoRa mesh yet | User | Open | Assemble NODE_02 and NODE_03 with same wiring/firmware as NODE_01 when hardware arrives.
I014 | Hardware | Implement rpicam/libcamera capture pipeline for Raspberry Pi Camera Rev 1.3 | Daytime camera feeds unavailable in production until CSI pipeline is integrated | Codex/User | Open | In Progress | modules/csi_camera_stream.py implemented; multi_camera_stream.py updated; app.py/config updated; pending deploy to .51/.52
I015 | Hardware | .53 NODE_02 and .54 NODE_03 CSI camera physical confirmation pending | Cannot confirm ov5647 detection on .53/.54 until hardware is powered and cabled | User | Open | Run rpicam-hello --list-cameras on .53 and .54 when ready.
I015 | Hardware | .53 NODE_02 and .54 NODE_03 CSI camera physical confirmation pending | Cannot confirm ov5647 detection on .53/.54 until hardware is powered and cabled | User | Open | Run rpicam-hello --list-cameras on .53 and .54 when ready.
I017 | Integration | MAIN ESP32 USB serial reader implemented but not yet deployed/verified on .51 MAIN | Dashboard sensor cards may still use HTTP fallback until serial is validated in live mode | Codex | Open | Code deployed to .51; LIVE dashboard sensor-card population from serial cache NOT YET VERIFIED. Blocked by .51 unavailability.
I018 | Hardware | .53 NODE_02 and .54 NODE_03 hardware build pending | Cannot validate full 4-node LoRa mesh or camera grid until ESP32 + sensors + LoRa are assembled | User | Open | Assemble NODE_02/NODE_03 using NODE_01 baseline; run LoRa bench test. RPi CSI cameras are already operational.
I019 | Hardware | Thermal camera (MLX90640) not yet physically installed on MAIN | Thermal night detection feature unavailable until hardware is mounted and wired | User | Open | Install MLX90640 on MAIN RPi I2C and validate /thermal_feed endpoint.
I020 | Audio | USB microphone not installed on any node; chainsaw detection pipeline untested | Audio alert and event recording features cannot be validated in live mode | User/Codex | Open | Install USB microphone on a node, run detector.py with field audio or synthetic test clips, validate score threshold and recording trigger.

## Decision Log
Decision Log
Approved decisions and evidence.
Decision ID | Date | Decision | Rationale | Evidence | Impact
D001 | 2026-05-15 | Main server is physically installed on the center/backup field node | User clarified placement | User answer #1 | Center node combines receiver/dashboard/thermal.
D002 | 2026-05-15 | Remote nodes are Raspberry Pi + ESP32 nodes | Chainsaw/audio processing needs RPi | User answer #2 | Node BOM includes RPi and ESP32.
D003 | 2026-05-15 | Use existing RPi chainsaw detector as baseline and improve it | Current code already works | User answer #3 and detector.py | No ESP32-only audio model for baseline.
D004 | 2026-05-15 | Every node and main server has a daytime camera | User clarified final camera coverage | User answer #4 | Dashboard must show all feeds.
D005 | 2026-05-15 | Every node/main server has a 12V battery system | User clarified power | User answer #5 | Power design includes buck converters and voltage telemetry.
D006 | 2026-05-15 | LoRa for sensors, Wi-Fi for camera/dashboard | Meeting and PDF align | Zoom transcript | Hybrid design.
D007 | 2026-06-02 | Raspberry Pi Camera Rev 1.3 (ov5647) via CSI is the official daytime camera hardware | USB webcam produced corrupted/distorted frames on RPi 3B; CSI camera is native, reliable, and already detected | rpicam-hello --list-cameras shows ov5647 on .51 and .52 | All nodes use CSI ribbon camera; USB path deprecated but code fallback preserved temporarily.
D008 | 2026-06-02 | USB webcam path is deprecated from target design | YUYV fails outright; MJPG works but frames are corrupted on RPi 3B due USB bandwidth/power limits | Camera test history and rpicam-hello detection results | Historical USB findings remain documented for reference only.
D007 | 2026-06-02 | Raspberry Pi Camera Rev 1.3 (ov5647) via CSI is the official daytime camera hardware | USB webcam produced corrupted/distorted frames on RPi 3B; CSI camera is native, reliable, and already detected | rpicam-hello --list-cameras shows ov5647 on .51 and .52 | All nodes use CSI ribbon camera; USB path deprecated but code fallback preserved temporarily.
D008 | 2026-06-02 | USB webcam path is deprecated from target design | YUYV fails outright; MJPG works but frames are corrupted on RPi 3B due USB bandwidth/power limits | Camera test history and rpicam-hello detection results | Historical USB findings remain documented for reference only.
D010 | 2026-06-08 | MAIN .51 dashboard operates in LIVE mode with CSI camera and ESP32 serial integration | .51 is the field main server; simulation mode is no longer the primary runtime; CSI camera provides stable daytime feed; serial provides local ESP32 data | Dashboard validation on .51; rpicam-hello and minicom confirmations | LIVE mode is the default for .51; simulation remains available for local development.
D011 | 2026-06-08 | .53 and .54 remain in pending hardware state; no remote ESP32 assembly yet | CSI cameras are installed but ESP32 + LoRa + sensor wiring is not assembled; cannot proceed with node validation | Hardware inventory status | NODE_02/NODE_03 assembly is the next hardware milestone after MAIN/NODE_01 are fully validated.
D012 | 2026-06-08 | Thermal camera and USB microphone are retained in design but deferred until hardware is available | MLX90640 and USB mic are in BOM and code; field validation blocked by physical installation | Design documents and code baseline already include thermal and audio modules | Install thermal on MAIN first; install USB mic on one node for chainsaw validation.
D010 | 2026-06-09 | Separate NODE GUI vs shared dashboard.html | NODE RPis need a simplified one-page dashboard without server-specific cards; MAIN dashboard must remain full-featured | Maintainability and role-appropriate UX | app.py index() routes by role; node_dashboard.html is one-page; dashboard.html unchanged for MAIN

## Risk Register
Risk Register
Implementation risks and mitigations.
Risk | Category | Likelihood | Impact | Mitigation | Owner | Status
LoRa packet loss in forest line-of-sight conditions | Networking | Medium | High | Use RSSI/SNR logging, retries, ACKs, antenna placement, PDR test | Codex/User | Open
Wi-Fi camera streams overload field router | Networking | Medium | Medium | Limit FPS/resolution, use camera grid lazy loading, local AP placement | Codex/User | Open
False chainsaw positives from engines/wind/rain | AI/Audio | Medium | Medium | Calibrate detector, collect field clips, add confidence smoothing | Codex/User | Open
MQ2 drift and high heater power | Sensor | High | Medium | Warm-up/calibration, analog reading, threshold tuning, power budget | User | Open
Battery brownout resets RPi | Power | Medium | High | Use 5V 5A buck, fuse, low-voltage cutoff, voltage telemetry | User | Open
Water ingress in field enclosure | Mechanical | Medium | High | IP-rated enclosure, cable glands, desiccant, drip loops | User | Open
Thermal FOV misses event because only one camera | Thermal | Medium | Medium | Place center node strategically; use normal cameras and sensor alerts for coverage | User | Accepted
No GitHub remote delays off-machine backup | Process | High | High | Repo created and project baseline pushed | User/Codex | Resolved

## System Diagram
System Diagram
Text workbook equivalent of the architecture diagram.
Node | Role | Hardware | LoRa Link | Wi-Fi Link | Camera | Thermal | Notes
node-main-center | Main server + backup/center node | RPi + ESP32 + LoRa gateway + sensors + mic + siren relay | Receives telemetry from all nodes; may send ACK | Hosts dashboard/AP/router connection | Daytime camera | MLX90640 only here | Physically installed in field center.
node-01 | Remote sensor/camera node | RPi + ESP32 + LoRa + DHT/MQ2/mic | Sends telemetry/alerts | Streams camera to main | Daytime camera | None | RPi runs chainsaw detector.
node-02 | Remote sensor/camera node | RPi + ESP32 + LoRa + DHT/MQ2/mic | Sends telemetry/alerts | Streams camera to main | Daytime camera | None | RPi runs chainsaw detector.
node-03 | Remote sensor/camera node | RPi + ESP32 + LoRa + DHT/MQ2/mic | Sends telemetry/alerts | Streams camera to main | Daytime camera | None | RPi runs chainsaw detector.
dashboard-client | Viewer | Phone/tablet/laptop | None | Connects to field Wi-Fi and opens main RPi IP | Views all feeds | Views main thermal | No direct node control required.

## Data Flow
Data Flow
Operational sequence from sensing to alerting.
Step | Actor | Input | Processing | Output | Target | Timing
1 | ESP32 | DHT/MQ2/battery sensors | Read/filter/average | Sensor snapshot | RPi/LoRa packet builder | Every 2-10 sec local
2 | RPi node | Microphone audio | FFT/RMS/mechanical-band chainsaw detection | chainsaw_score/detected | Packet builder + local event | 1 sec windows
3 | RPi node | Camera frame | MJPEG stream and optional recording | Video feed/clip | Main dashboard/media | 8-10 FPS
4 | Node LoRa | Telemetry JSON/compact packet | Send with seq | LoRa packet | Main gateway | Every 60 sec or alert immediate
5 | Main LoRa gateway | LoRa packet | Validate, timestamp, attach RSSI/SNR | DB reading/event | SQLite/API | On receive
6 | Alert engine | Readings/events | Rules for smoke/fire/chainsaw/thermal | Alert state | Dashboard/siren | Under 5 sec target
7 | Dashboard | API/SSE/camera streams | Render current state | Operator view | Phone/laptop | Live + 1 min data cadence

## Codex GitHub Workflow
Codex GitHub Workflow
Required workflow for keeping code and workbook synchronized.
Step | Action | Command / Tool | Workbook Update | GitHub Requirement | Status
1 | Initialize local repo | git init | Progress + Change Log | Local repo created; remote still required | Done locally
2 | Provide target GitHub repo and branch | User supplies owner/repo + branch | Update README and Dashboard | Repo created: pagibetech/adm-firenode-forest-monitoring | Done
3 | Import current code artifacts | Unzip RPi code, add ESP32 firmware | Progress Tracker | Commit code baseline | Done locally
4 | Place workbook in docs/workbook | docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx | This workbook | Commit workbook with code | Done locally
5 | Every major step | Edit code, run tests, update workbook | Progress/Change/Issue/Decision logs | Commit together | Policy
6 | Open PR or push branch | GitHub connector or git push | Record commit/PR link | Baseline pushed to main commit 05e1a77 | Done

## Codex Task Prompts
Codex Task Prompts
Reusable prompts so future chat sessions can continue without losing context.
Prompt Name | Use When | Prompt Text
Resume Project | New chat/session | Read docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx first. Treat it as the source of truth. Summarize current status, blockers, next step, and latest decisions before editing code.
Update Workbook After Step | After any major implementation step | Update Progress Tracker, Change Log, Decision Log or Issue Log, and any affected technical sheet. Include date, evidence, files changed, tests run, and next action.
Implement Next Step | Coding session | Use the workbook Phase Plan and Detailed Steps. Implement the first unblocked Not Started/In Progress task, run relevant tests, then update workbook and prepare GitHub commit.
Field Test Recording | After hardware test | Add field test results to Test Campaign with date, node, test ID, measured values, pass/fail, photos/log references, and issues discovered.
GitHub Sync | Before ending work | Confirm git status, commit code and workbook together, push to the agreed branch, and record commit hash/PR link in Change Log.

## Active Context Snapshot
Active Context Snapshot
Rapid recovery snapshot for model switching, broken chats, and low-cost continuation.
Field | Current Value | Notes
Project | ADM FireNode Forest Monitoring System | Hybrid LoRa + Wi-Fi forest fire/logging monitoring prototype.
Repo | https://github.com/pagibetech/adm-firenode-forest-monitoring | GitHub main currently contains baseline without CI workflow due token workflow-scope limit.
Local Repo Path | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | Use workbook + repo before any implementation.
Workbook | docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx | Persistent project memory.
Current Branch | main | Local branch has full history; remote main has pushed project snapshot.
Latest Completed Step | MAIN .51 dashboard LIVE mode; CSI cameras validated on .51/.52/.53/.54; remote node aggregation .51→.52 PASS; ESP32 serial reader implemented; minicom confirmed hardware; NODE_02/NODE_03 CSI alignment completed. | 2026-06-09
Current Active Milestone | MAIN ESP32 USB serial integration verification (pending .51 availability) | Next: resume when .51 is reachable and validate live sensor cards from serial.
Current Active Feature | CSI camera pipeline LIVE on .51/.52/.53/.54; ESP32 serial integration implemented pending .51 verification | No new features until serial validation resumes and remaining hardware are validated.
Latest Unresolved Issue | MAIN ESP32 dashboard live sensor integration pending verification (blocked by .51 unavailability); NODE_02/NODE_03 ESP32 hardware build pending; thermal and audio pending hardware. | Serial code is complete; NODE_02/NODE_03 CSI cameras are operational.
Testing State | CSI camera .51/.52/.53/.54 PASS; remote aggregation PASS; serial hardware PASS; serial dashboard integration PENDING (blocked by .51 unavailability). | Pending: .51 availability to deploy serial reader and confirm sensor card population.
Recommended Tool Now | Local machine / hardware bench | Use VS Code + Roo Code + Kimi for small edits; local machine for flashing, serial monitor, and hardware testing.
Current Milestone | Hardware bench validation extended: MAIN + NODE_01 camera and network validated; NODE_02/NODE_03 CSI cameras validated; serial code ready | Focus on .51 availability and sensor verification.
Next Recommended Action | Resume when MAIN .51 is reachable: deploy updated raspi/firenode-system and validate live mode sensor cards from serial cache | Use SSH key ~/admfire and user betech against 192.168.9.51.
Next Incomplete Task | Verify MAIN ESP32 USB serial integration on .51 MAIN (blocked by .51 unavailability) | Confirm /api/status serial_connected=true and sensor values match minicom packets.
Paused Work | None (ESP32/LoRa hardware validation resumed via serial path) | Previous pause lifted; serial integration now active.
Current Issue | MAIN ESP32 serial integration implemented but not yet verified in live mode (blocked by .51 unavailability) | Code complete; minicom confirmed hardware output; NODE_02/NODE_03 CSI cameras operational.
Next Recommended Action | Resume when MAIN .51 is reachable: deploy updated raspi/firenode-system and validate live mode sensor cards from serial cache | Use SSH key ~/admfire and user betech against 192.168.9.51.
Camera Stability Default | CSI: 640x480, 15 FPS, JPEG quality 85. USB fallback preserved: 320x240, 10 FPS, JPEG quality 55, MJPG, 10 warmup frames. | CSI validated on .51/.52/.53/.54 in LIVE mode.

## AI Session Handoff
AI Session Handoff
Current assumptions, unfinished work, and model handoff guidance.
Item | Status | Owner / Tool | Expected Output
Unfinished: push CI workflow | Pending | Local machine or Codex after workflow scope | .github/workflows/ci.yml on GitHub.
Unfinished: PlatformIO firmware build | Pending | Local machine / VS Code PlatformIO | Build logs for firmware/esp32-firenode and firmware/esp32-lora-gateway.
Unfinished: hardware validation | Partial | Local machine + hardware bench | LoRa RSSI/SNR/PDR logs, camera feed screenshots, recording evidence.
Active assumption | Only one MLX90640 thermal camera on main/center node | Workbook decision D001/D004 | Remote nodes use daytime cameras only.
Active assumption | Remote nodes are Raspberry Pi + ESP32 | Workbook architecture | RPi handles camera/audio; ESP32 handles sensor/LoRa.
Pending workbook update | Only after major validation or config change | Selected AI/tool | Concise Progress/Issue/Build Matrix update.
Recommended next model | Local machine first; Kimi for heavy implementation; Codex for repo execution/validation | AI Router | Avoid premium Codex for docs/simple edits.
Unfinished: run automated RPi deployment | NODE_02/NODE_03 CSI cameras validated; MAIN ESP32 serial pending .51 availability | Selected AI/tool | ./scripts/deploy_all_rpis.sh output, API responses, and stream placeholder checks
Active assumption | Local machine first; Kimi for heavy implementation; Codex for repo execution/validation | AI Router | Use simulation mode support on all RPis until hardware validation resumes
Next command | Partial | Local machine / MacBook terminal | ./scripts/deploy_all_rpis.sh; then inspect logs/deploy_*.log and validate dashboard/API
Unfinished: validate main-server camera fix | NODE_02/NODE_03 CSI validated; MAIN camera fix validated; low-bandwidth defaults no longer needed (CSI) | Local MacBook + Main RPi | Targeted redeploy, camera_test.py output, /video_feed response, dashboard screenshot
Unfinished: validate low-bandwidth camera defaults | Completed (CSI replaces USB) | Local MacBook + Main RPi | Deploy to 192.168.9.51, run camera_test.py at 320x240/10 FPS, inspect dashboard image clarity

## Prompt Library
Prompt Library
Reusable prompts for low-cost model routing and continuation.
Prompt Name | Recommended Tool | Prompt
Roo/Kimi Implementation | Kimi K2.6 via Roo Code | Read workbook Active Context Snapshot and AI Session Handoff. Implement the next incomplete milestone only. Inspect only affected files. Report changed files and validation steps.
DeepSeek Medium Fix | DeepSeek V3 via Roo Code | Make a targeted medium-complexity code change. Avoid repo-wide scans. Preserve architecture and report exact files changed.
Gemini Documentation | Gemini/Gemma API | Draft concise documentation/workbook text for the specified section. Do not modify code. Keep output structured and low-token.
Codex Task | Codex | Use only for repo execution/validation. Include project context, objective, scope, validation commands, workbook update rule, and required output.
Local Qwen Emergency | LM Studio Qwen | Offline fallback only. Make a one-file/simple fix or draft note. Do not attempt full repo analysis.
Hardware Validation Report | Local machine / technician | Run the specified hardware test and return logs, screenshots, device paths, pass/fail, and measured values for workbook entry.

## Build Validation Matrix
Build Validation Matrix
Current component build/runtime/deployment validation state.
Component | Build Status | Runtime Status | Deployment Status | Latest Test Result | Validation Command | Remaining Issue
Raspberry Pi Flask app | Pass | Pass in simulation | Local only | Unit tests OK; smoke test OK | ./scripts/run_raspi_tests.sh; ./scripts/smoke_test_main_simulation.py | Hardware deployment pending
LoRa packet store/API | Pass | Pass in simulation | Local/GitHub | Stored packet history verified | /api/lora/status; /api/lora/packets | Real serial gateway hardware pending
Event recording | Pass | Pass for snapshot metadata | Local/GitHub | Recording tests OK | ./scripts/run_raspi_tests.sh | Full video clip recording future enhancement
ESP32 sensor sender firmware | Pass | Pass on MAIN/NODE_01 bench | GitHub/local | DHT22/PIR/MQ/LoRa TX validated on MAIN and NODE_01 | pio run (firmware/esp32-firenode) | NODE_02/NODE_03 hardware pending
ESP32 LoRa gateway firmware | Pass | Pass on MAIN bench | GitHub/local | LoRa two-way MAIN↔NODE_01 PASS (RSSI -29 to -35 dBm; SNR 9.25-10.00) | pio run (firmware/esp32-lora-gateway) | NODE_02/NODE_03 hardware pending
GitHub CI workflow | Present locally | Not on GitHub | Local only | Workflow file present; push blocked by token scope | git push | Need token with workflow scope; not blocking bench validation
Automated Raspberry Pi deployment scripts | Pass | Not yet run on RPis | Ready for MacBook execution | Shell syntax check passed | bash -n scripts/deploy_main_server.sh scripts/deploy_node.sh scripts/deploy_all_rpis.sh | Needs live RPi deployment validation
Automated RPi deployment orchestration v2 | Pass | Not yet run on RPis | Ready for MacBook execution | Syntax/help/unit/smoke validation passed | bash -n; ./scripts/deploy_all_rpis.sh --help; ./scripts/run_raspi_tests.sh; ./scripts/smoke_test_main_simulation.py | Needs live RPi deployment validation
RPi USB camera MJPG/V4L2 capture fix | Pass local compile/tests | Pass on RPi 3B with MJPG but corrupted frames | Ready for targeted main-server redeploy | camera_test.py runs; frames distorted/corrupted at all settings | python3 -m py_compile; ./scripts/run_raspi_tests.sh; ./scripts/smoke_test_main_simulation.py | Camera replacement or powered USB hub recommended before field deployment
RPi 3B camera stability defaults | Pass local compile/tests | Pass on RPi 3B with MJPG but corrupted frames | Ready for targeted main-server redeploy | Low defaults applied; corruption persists | py_compile; unit tests; smoke test; camera_test --help | Hardware compatibility blocker; camera replacement or powered USB hub recommended
RPi USB camera MJPG/V4L2 capture fix | Pass local compile/tests | Deprecated; USB path removed from target design | N/A | Replaced by CSI camera plan | python3 -m py_compile; ./scripts/run_raspi_tests.sh | Superseded by CSI camera implementation (P042).
RPi 3B camera stability defaults | Pass local compile/tests | Deprecated; USB path removed from target design | N/A | Replaced by CSI camera plan | py_compile; unit tests; smoke test | Superseded by CSI camera implementation (P042).
Raspberry Pi Camera Rev 1.3 CSI detection | N/A (hardware) | Pass on .51/.52/.53/.54 | Pass | ov5647 detected on .51/.52/.53/.54; rpicam-hello confirmed | rpicam-hello --list-cameras | Detection confirmed on all nodes.
RPi USB camera MJPG/V4L2 capture fix | Pass local compile/tests | Deprecated; USB path removed from target design | N/A | Replaced by CSI camera plan | python3 -m py_compile; ./scripts/run_raspi_tests.sh | Superseded by CSI camera implementation (P042).
RPi 3B camera stability defaults | Pass local compile/tests | Deprecated; USB path removed from target design | N/A | Replaced by CSI camera plan | py_compile; unit tests; smoke test | Superseded by CSI camera implementation (P042).
Raspberry Pi Camera Rev 1.3 CSI detection | N/A (hardware) | Pass on .51/.52/.53/.54 | Pass | ov5647 detected on .51/.52/.53/.54; rpicam-hello confirmed | rpicam-hello --list-cameras | Detection confirmed on all nodes.
Raspberry Pi Camera Rev 1.3 CSI pipeline (Picamera2) | Pass local compile/tests | Pass on .51/.52/.53/.54 | Pass | modules/csi_camera_stream.py + multi_camera_stream.py + app.py updates; py_compile passed; validated on all nodes | python3 -m py_compile; deploy to .51/.52; curl /video_feed | CSI primary with USB fallback; simulation preserved.
CSI camera validation .51 | N/A (hardware) | Pass on .51 | Pass | MAIN .51 dashboard LIVE mode; CSI feed clear and stable | Visual inspection on dashboard; rpicam-hello --list-cameras; curl /video_feed | None.
CSI camera validation .52 | N/A (hardware) | Pass on .52 | Pass | NODE_01 .52 CSI feed visible on MAIN dashboard | Visual inspection on MAIN dashboard remote camera grid; rpicam-hello on .52 | None.
Remote node aggregation .51 to .52 | Pass local compile/tests | Pass on .51/.52 network | Pass | MAIN discovers NODE_01; remote slot 1 populated with sensor and camera data | Dashboard inspection; /api/server-dashboard JSON verification | None for .52; .53/.54 pending hardware.
MAIN ESP32 USB serial reader | Pass local compile/tests | Pending hardware validation on .51 | In Progress | modules/esp32_serial_reader.py; parsing unit test passed; py_compile passed; minicom confirmed hardware output | python3 -m py_compile; manual parse_line test; minicom on /dev/ttyUSB0 115200 | Dashboard sensor overlay not yet verified in live mode; HTTP fallback preserved.
MAIN ESP32 serial hardware confirmation | N/A (hardware) | Pass on .51 bench | Pass | Minicom shows readable packets at 115200; NODE=MAIN and NODE=NODE_01 lines observed | minicom -D /dev/ttyUSB0 -b 115200 | Code deployed but live dashboard integration pending verification.
.53 NODE_02 / .54 NODE_03 hardware build | N/A | Pending hardware assembly | Not Started | CSI cameras installed; ESP32 + LoRa + sensors not yet assembled | Physical inventory and assembly checklist | Use NODE_01 wiring/firmware baseline for assembly.
Thermal camera (MLX90640) installation | N/A | Pending hardware installation | Not Started | Module exists in code; not physically installed on MAIN | Physical installation on MAIN RPi I2C; verify /thermal_feed | Deferred until thermal hardware is available.
Chainsaw detection / USB microphone | Pass local compile/tests | Pending hardware installation | Not Started | detector.py baseline and test audio exist; no live microphone connected | python3 -m py_compile; synthetic test audio validation | Deferred until USB microphone is installed on a node.
Raspberry Pi CSI camera pipeline (Picamera2) | Pass local compile/tests | Pass on .51/.52/.53/.54 | Pass | modules/csi_camera_stream.py + multi_camera_stream.py + app.py updates; py_compile passed; validated on all nodes | python3 -m py_compile; deploy to .51/.52/.53/.54; curl /video_feed | CSI primary with USB fallback; simulation preserved.
CSI camera validation .53 | N/A (hardware) | Pass on .53 | Pass | NODE_02 .53 dashboard in LIVE mode; CSI feed clear and stable | Visual inspection on dashboard; rpicam-hello --list-cameras; curl /video_feed | Required python3-picamera2 and file sync.
CSI camera validation .54 | N/A (hardware) | Pass on .54 | Pass | NODE_03 .54 dashboard in LIVE mode; CSI feed clear and stable | Visual inspection on dashboard; rpicam-hello --list-cameras; curl /video_feed | Required python3-picamera2 and sync of modules/multi_camera_stream.py.
python3-picamera2 package dependency | N/A | Required on .53/.54 | Pass | sudo apt install -y python3-picamera2 | dpkg -s python3-picamera2 | Not preinstalled on fresh RPi OS Lite; required for Picamera2 CSI stream.
Deployment sync checklist (CSI alignment) | N/A | Required for .53/.54 | Pass | app.py, static/app.js, templates/dashboard.html, modules/csi_camera_stream.py, modules/multi_camera_stream.py, config.json, .deployment.env | rsync / deploy scripts | Ensure node-specific config values (name, IP, role) are correct per node.
Node dashboard (node_dashboard.html + node_app.js) | Pass local py_compile and role routing logic | Pending deployment to .52/.53/.54 | In Progress | templates/node_dashboard.html, static/node_app.js; app.py updated | python3 -m py_compile app.py modules/*.py | One-page NODE GUI with camera, sensors, chainsaw, alerts, recordings.

## Environment Snapshot
Environment Snapshot
Known local/toolchain environment details.
Item | Value | Notes
Current Date | 2026-05-15 | Asia/Manila workflow date.
Local Python | Python 3.12.11 | Observed via python3 --version.
Bundled Node | v24.14.0 | Codex workspace runtime.
PlatformIO | Not found locally | Install locally or rely on GitHub CI after workflow scope.
GitHub Repo | pagibetech/adm-firenode-forest-monitoring | Private repo created by user.
Remote main | b09c2c6 | Remote baseline + GitHub sync workbook checkpoint.
Local full-history branch | local-full-history-with-ci | Preserves workflow file and detailed local commits.
Roo Profiles Needed | Kimi Main; DeepSeek Cheap; Gemini Online; Local Qwen Emergency | Configure in VS Code/Roo Code.

## AI Stack
AI Stack
Model/tool roles, routing, cost category, and limitations.
Tool / Model | Provider / Source | Purpose | Cost Category | Use When | Do Not Use For | Roo Profile / Fallback | Notes
ChatGPT | OpenAI ChatGPT | Project director, planning, architecture, debugging strategy | Moderate | Milestone planning, prompts, troubleshooting | Repeated repo execution/build loops | N/A | Directs work and prepares Codex/Roo tasks.
Kimi K2.6 | Roo Code cloud model | Primary heavy implementation and long-context coding | Paid but lower-cost than premium execution | Architecture-aware multi-file implementation | Local runtime validation | Kimi Main | Use before Codex when direct execution is not required.
DeepSeek V3 | Roo Code cloud model | Cheap coding backup and medium implementation | Low | Medium edits, utility code, doc refinement | High-risk repo-wide changes | DeepSeek Cheap | Escalate to Kimi if context/complexity exceeds capability.
Gemini / Gemma API | Google AI Studio/API | Low-cost docs, summaries, simple notes, prompt cleanup | Free/low | Documentation and lightweight planning | Complex repo-aware implementation | Gemini Online | Preferred for workbook text drafts.
Codex | OpenAI Codex | Premium repo execution, tests, validation, difficult multi-file fixes | Premium | Terminal validation, dependency-aware debugging, focused repo edits | Simple docs/snippets/workbook-only work | N/A | Use sparingly with exact scope and validation command.
Local Qwen via LM Studio | Local offline model | Emergency offline fallback | Local/free | Internet/API outage, one-file/simple fixes | Autonomous repo-wide tasks | Local Qwen Emergency | Avoid heavy agent mode.

## AI Router
AI Router / Model Routing Rules
Cheapest-capable model routing and escalation rules.
Task Type | Recommended Model / Tool | Reason | Escalation Target | Cost Level | Allowed Scope | Prohibited Use | Example Prompt
Documentation/simple explanation | Gemini/Gemma API | Cheap and sufficient | DeepSeek V3 | Low | Docs, notes, workbook text | Repo-wide code edits | Draft concise deployment notes for this section.
Medium coding | DeepSeek V3 | Cheap general coding | Kimi K2.6 | Low/Medium | Small multi-file or utility edits | Hard debugging with live execution | Implement targeted parser fix in these files only.
Heavy architecture-aware coding | Kimi K2.6 | Long context and stronger implementation | Codex | Medium/High | Large feature design and code generation | Running local tests/builds | Implement milestone X using workbook context.
Repo execution/testing/validation | Codex | Requires terminal and actual repo state | Local machine/manual | Premium | Focused commands and code fixes | Simple docs/snippets | Run specified tests, fix failures, update workbook if major.
Builds/flashing/hardware | Local machine | Primary execution environment | Codex only for script fixes | No AI cost | PlatformIO, Arduino IDE, SSH, hardware logs | Cloud AI autonomous hardware loops | Run pio and return logs.
Offline emergency | Local Qwen | No internet/API needed | Wait for online model | Local/free | One-file/simple fixes | Full repo analysis | Patch this syntax issue only.

## AI Model Routing Log
AI Model Routing Log
Record important model/tool routing decisions.
Date | Task | Selected Model / Tool | Reason Selected | Result | Escalation Needed | Next Recommended Tool
2026-05-15 | Update workbook with hybrid low-cost AI workflow sheets | Codex | User explicitly requested direct workbook update in current repo | Workbook sheets added/updated | No | Gemini/Gemma or DeepSeek for future workbook-only drafts
2026-05-15 | Future PlatformIO firmware build | Local machine | Build/flashing belongs to local execution environment | Pending | Only if build fails | Codex for focused failure fix
2026-05-15 | Future hardware validation | Local machine / hardware bench | Requires devices, serial monitor, camera, LoRa, batteries | Pending | No AI escalation until logs exist | ChatGPT for analysis or Codex for repo fix

## Codex Task Log
Codex Task Log
Track premium Codex usage, commands, files, validation, and commits.
Date | Task | Repo Path | Files Changed | Commands Run | Validation Result | Unresolved Issues | Workbook Update | Git Commit
2026-05-15 | Add hybrid low-cost AI workflow sheets | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx | Workbook build/verify/render | Pending final push | CI workflow scope still blocked | Yes | Pending
2026-05-15 | GitHub baseline sync | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | Project snapshot and workbook | git push via scoped-safe temp repo | Remote main b09c2c6 | Workflow file not pushed | Yes | b09c2c6 remote
2026-05-20 | Create automated Raspberry Pi deployment scripts for simulation-mode deployment | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | scripts/deploy_main_server.sh; scripts/deploy_node.sh; scripts/deploy_all_rpis.sh; docs/deployment/rpi_automated_deployment.md; workflow memory docs; workbook | bash -n deployment scripts; deploy_node --help | Local script validation passed; live RPi deployment pending | ESP32/LoRa hardware validation paused; GitHub CI workflow scope issue may remain | Yes
2026-05-20 | Update RPi deployment scripts for parallel/sequential/targeted deployment and role labels | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | scripts/deploy_all_rpis.sh; scripts/deploy_node.sh; scripts/deploy_main_server.sh; raspi/firenode-system/app.py; docs/deployment/rpi_automated_deployment.md; workflow docs; workbook | bash -n; deploy_all --help; deploy_node --help; py_compile app.py; run_raspi_tests.sh; smoke_test_main_simulation.py | Passed locally; live RPi deployment pending | ESP32/SX1278 validation paused due wiring/power instability | Yes
2026-05-21 | Fix Raspberry Pi USB camera capture format for main-server /dev/video0 | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | camera_stream.py; camera_test.py; config.json; app.py; README/deployment docs; workflow docs; workbook | py_compile; run_raspi_tests.sh; smoke_test_main_simulation.py; camera_test.py --help; bash -n deployment scripts | Passed locally; live RPi camera validation pending | ESP32/LoRa validation remains paused | Yes
2026-05-21 | Lower RPi 3B USB camera defaults for stability | /Users/macbookm1max321tb/A_Design/A_Coding/ADM Fire | camera defaults/config/docs/workbook | py_compile; run_raspi_tests.sh; smoke_test_main_simulation.py; camera_test.py --help; bash -n deploy scripts | Passed locally; live RPi validation pending | Live RPi validation required | Yes

## Software Dependencies
Software / Dependency Tracker
Runtime and toolchain dependency state.
Component | Dependency | Required Version / Source | Current Status | Install / Validation Command | Notes
Raspberry Pi app | Python | 3.x on Raspberry Pi OS | Local Python 3.12.11 observed | python3 --version | RPi target may differ.
Raspberry Pi app | Flask, requests, Pillow, pyserial | requirements.txt | Configured | pip install -r requirements.txt | OpenCV/sounddevice normally installed via setup/apt.
ESP32 firmware | PlatformIO | Latest compatible | Not installed locally | pio run | Install in VS Code/PlatformIO.
ESP32 firmware | LoRa library | sandeepmistry/LoRa | Configured | pio run | Used by sender and gateway.
Workbook | @oai/artifact-tool | Codex bundled spreadsheet runtime | Available in Codex | Workbook builder/verify | Used only for workbook generation.
Raspberry Pi CSI camera | python3-picamera2 | Latest available via apt | Required on .53/.54; confirmed installed | sudo apt install -y python3-picamera2 | Not preinstalled on RPi OS Lite; required for Picamera2 CSI stream.

## Simulation Plan
Simulation Plan
Current simulation coverage and next validation steps.
Area | Current Simulation Coverage | Validation Command / Endpoint | Status | Next Step
Dashboard | Main + 3 remote simulated nodes | ./scripts/smoke_test_main_simulation.py | Pass | Use for demos before hardware.
Camera | PIL fallback local camera + remote simulated feeds | /video_feed/0; dashboard | Pass | Validate real camera hardware on RPi.
Thermal | MLX90640 simulation fallback | /thermal_feed | Pass | Validate real MLX90640 on main node.
LoRa | Simulated packets with seq/RSSI/SNR/PDR/battery | /api/lora/status | Pass | Validate ESP32 gateway serial bridge.
Recording | Snapshot metadata on chainsaw event path | /api/recordings | Pass | Validate real chainsaw trigger and camera snapshot.

## Validation Procedures
Validation Procedures
Procedures for local, CI, and hardware validation.
Validation | Where To Run | Command / Procedure | Expected Result | Evidence To Save
Python unit tests | Local machine or CI | ./scripts/run_raspi_tests.sh | All tests OK | Terminal output
Simulation smoke test | Local machine | ./scripts/smoke_test_main_simulation.py | 4 dashboard nodes and 4 LoRa nodes | Terminal output
Firmware build | Local machine / PlatformIO | pio run in each firmware folder | Build success | Build logs
LoRa bench test | Hardware bench | Run sender + gateway + lora_gateway_serial.py | Packets stored in /api/lora/packets | RSSI/SNR/PDR logs
Field test | Deployment site | Run Test Campaign T001-T010 | Pass/fail per test | Workbook Test Campaign evidence
Automated RPi script syntax | MacBook local repo | bash -n scripts/deploy_main_server.sh scripts/deploy_node.sh scripts/deploy_all_rpis.sh | No syntax errors | Terminal output
RPi deployment execution | MacBook local repo | ./scripts/deploy_all_rpis.sh | All four RPis receive app files, venv, config.json, and optional service file | Terminal output and per-node deployment logs
Simulation/API validation | MacBook after manual start | curl http://192.168.9.51:8090/api/status; curl http://192.168.9.51:8090/api/server-dashboard; curl http://192.168.9.52:8090/api/node-data | Simulation mode API returns valid JSON and dashboard sees configured nodes | Terminal output or screenshots
Stream placeholder validation | MacBook after manual start | curl -I --max-time 5 http://192.168.9.51:8090/video_feed; curl --output /tmp/firenode-thermal.png http://192.168.9.51:8090/thermal.png | Camera route responds and main thermal placeholder PNG is generated | Headers and PNG file output
Parallel RPi deployment | MacBook local repo | ./scripts/deploy_all_rpis.sh | All four RPis deploy in parallel and logs are written under logs/deploy_<ip>.log | Final PASS/FAIL summary and per-IP logs
Sequential RPi deployment | MacBook local repo | ./scripts/deploy_all_rpis.sh --sequential | Each RPi deploys one at a time with per-IP logs | Terminal output and logs
Single target RPi deployment | MacBook local repo | ./scripts/deploy_all_rpis.sh --target 192.168.9.52 | Only selected RPi deploys and summary reports one target | Target log file
RPi USB camera MJPG/V4L2 test | Main server RPi | ./venv/bin/python camera_test.py --device 0 --fourcc MJPG --width 640 --height 480 --fps 25 | Camera test passed and saves /tmp/firenode_camera_test.jpg | Terminal output and saved frame
Dashboard live camera route | MacBook after main server restart | curl -I --max-time 5 http://192.168.9.51:8090/video_feed | HTTP response from MJPEG stream and no Camera frame read failed status | curl output and dashboard screenshot
RPi 3B low-bandwidth USB camera test | Main server RPi | ./venv/bin/python camera_test.py --device 0 --fourcc MJPG --width 320 --height 240 --fps 10 | Camera test passes without corrupt/unclear image | Terminal output and /tmp/firenode_camera_test.jpg

## Known Issues
Known Issues
Open issues that affect workflow, validation, or deployment.
Issue | Severity | Status | Impact | Next Action
GitHub credential lacks workflow scope | Medium | Open | CI workflow not pushed to GitHub | Enable workflow scope or push CI with proper token/app.
PlatformIO unavailable locally | Medium | Resolved | PlatformIO 6.1.19 installed; builds pass | Firmware builds validated locally and on bench.
Battery chemistry/Ah unknown | Medium | Open | Runtime and low-voltage thresholds uncertain | Confirm exact battery specs.
Real hardware not connected | High | Partially resolved | MAIN + NODE_01 ESP32 bench validated; NODE_02/NODE_03 pending | Continue integration with validated MAIN + NODE_01 path; assemble NODE_02/NODE_03 when available.
Battery ADC on MAIN appears floating/unconnected | Medium | Open | Battery telemetry unavailable on MAIN | Verify voltage divider wiring and ADC pin assignment.
USB webcam compatibility blocker on RPi 3B | High | Resolved | Daytime camera feeds may be unavailable or corrupted in field | Replaced with Raspberry Pi Camera Rev 1.3 CSI. Historical USB findings remain documented for reference.
NODE_02/NODE_03 ESP32 hardware not assembled | Medium | Open | Cannot validate full 4-node LoRa mesh yet | Assemble with same wiring/firmware as NODE_01 when hardware arrives.
CSI camera pipeline not yet implemented | High | Resolved | Production camera feeds unavailable until rpicam/libcamera integration is complete | Picamera2 CSI pipeline implemented and validated on .51/.52. USB fallback preserved.
.53/.54 CSI camera physical confirmation pending | Low | Resolved | ov5647 detection confirmed on .53/.54; local dashboard streams validated. | Complete.
.53/.54 CSI camera physical confirmation pending | Low | Resolved | ov5647 detection confirmed on .53/.54; local dashboard streams validated. | Complete.
MAIN ESP32 dashboard live sensor integration not yet verified | Medium | Open | Sensor cards on MAIN dashboard may still show HTTP fallback data instead of serial cache until .51 is reachable and deployment validation is complete | Resume when .51 is reachable: deploy and verify /api/status serial_connected=true and sensor card values match minicom packets.
.53/.54 ESP32 + LoRa + sensor hardware build pending | High | Open | Cannot validate full 4-node mesh or complete ESP32 sensor integration until NODE_02/NODE_03 are assembled. RPi CSI cameras are already operational. | Assemble using NODE_01 baseline; run LoRa bench test.
Thermal camera (MLX90640) not installed on MAIN | Medium | Open | Night thermal detection feature unavailable for field demo until hardware is mounted | Install MLX90640 on MAIN RPi I2C and validate /thermal_feed endpoint.
USB microphone not installed; chainsaw detection untested | Medium | Open | Audio alert and event recording features cannot be validated in live mode without microphone hardware | Install USB microphone on a node and run detector.py with synthetic then field audio.

## Troubleshooting Logs
Troubleshooting Logs
Concise troubleshooting history and resolutions.
Date | Problem | Cause | Resolution | Evidence
2026-05-15 | GitHub push rejected for workflow file | HTTPS credential lacks workflow scope | Pushed code/workbook baseline without CI workflow; preserved CI locally | Remote main b09c2c6
2026-05-15 | Initial GitHub repo had placeholder README | GitHub created README on repo creation | Resolved by keeping full project README in pushed snapshot | README on remote project
2026-05-14 | Local camera unavailable without OpenCV | cv2 missing on Mac venv | Added PIL simulation fallback | /video_feed/0 smoke test

## Continuation Instructions
Continuation Instructions
How to resume with minimum context and lowest capable model.
Step | Action | Recommended Tool | Output
1 | Open workbook and read Active Context Snapshot + AI Session Handoff | Any model | Current state summary
2 | Check GitHub repo main and local branch status | Local machine | Confirm latest commit and dirty files
3 | Choose cheapest capable model using AI Router | ChatGPT/Roo | Model/tool selection
4 | Run local validation only when needed | Local machine | Logs/screenshots
5 | Use Codex only for focused repo execution/validation | Codex | Changed files + validation result
6 | Update workbook only after a major milestone/test/config change | Selected tool | Concise tracker/log rows

## Repo Structure
Repo Structure
Proposed GitHub repository layout.
Path | Purpose | Initial Source | Status | Notes
docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx | Living project reference | Created by Codex | Created Locally | Commit once repo exists.
docs/artifacts/ | PDF/PNG/meeting references or summaries | User artifacts | Pending | Avoid committing huge video unless desired; store transcript/summary.
firmware/esp32-firenode/ | ESP32 sensor + LoRa firmware | ESP/FireNode_ESP32_v5 | Pending | PlatformIO project.
raspi/firenode-system/ | Main/node Flask app | RPi v4 ZIP | Created Locally | Refactor role-specific config.
raspi/services/lora_gateway.py | Main LoRa receiver service | New | Pending | SPI or serial bridge.
raspi/services/recorder.py | Camera event recording worker | New | Pending | ffmpeg/OpenCV.
raspi/tests/ | Unit/integration tests | New | Pending | Mock hardware where possible.
.github/workflows/ci.yml | Python + PlatformIO CI | New | Pending | After repo exists.
README.md | Project overview and run instructions | New | Pending | Should link workbook.

## Change Log
Change Log
Chronological log of workbook/code changes.
Change ID | Date | Type | Summary | Files / Sheets | Tests / Verification | Git Commit / PR | Next Step
C001 | 2026-05-15 | Workbook | Created ADM FireNode implementation workbook from reference format and all gathered FireNode requirements | All workbook sheets | Workbook inspected/rendered locally | Pending GitHub repo | Provide repo/branch and commit workbook
C002 | 2026-05-15 | Repository | Initialized local Git repo, created clean baseline folders, imported RPi v4 app and ESP32 v5 firmware, added simulation start docs/script | .gitignore; README.md; raspi/; firmware/; simulation/; scripts/; docs/artifacts | python3 -m compileall -q raspi/firenode-system | 21004de | Run simulation baseline and push after remote is provided
C003 | 2026-05-15 | Simulation | Verified main dashboard starts in simulation mode with one main node and three simulated remotes; updated start script to use local venv when present | scripts/start_main_simulation.sh; raspi/firenode-system/config.json; Progress Tracker; Issue Log; Change Log | HTTP 200 /; /api/server-dashboard returned 4 nodes and 3 remotes | Pending commit | Implement cv2-free local camera simulation fallback
C004 | 2026-05-15 | Simulation | Added cv2-free PIL fallback for the main node camera in simulation mode and suppressed macOS hostname warning | modules/camera_stream.py; modules/network_utils.py; app.py; Progress Tracker; Issue Log; Change Log | compileall passed; /api/server-dashboard local camera running=true simulation=true; /video_feed/0 returned MJPEG | Pending commit | Implement LoRa packet simulation/receiver path
C005 | 2026-05-15 | LoRa Simulation | Added simulated LoRa receiver packet contract, dashboard fields, and API endpoint for RSSI/SNR/PDR/sequence/battery telemetry | modules/lora_simulator.py; app.py; static/app.js; simulation/README.md; scripts/start_main_simulation.sh; Progress Tracker; Change Log | compileall passed; /api/lora/status active_nodes=4; /api/server-dashboard includes lora packet for main node | Pending commit | Implement real LoRa receiver adapter and SQLite packet store
C006 | 2026-05-15 | LoRa Storage | Added SQLite LoRa packet store plus /api/lora/packets and /api/lora/ingest so simulated and future hardware packets share persistence | modules/lora_packet_store.py; app.py; simulation/README.md; Progress Tracker; Change Log | compileall passed; /api/lora/status stored_packet_count=8; /api/lora/packets returned rows | Pending commit | Implement real LoRa receiver adapter
C007 | 2026-05-15 | LoRa Gateway | Added serial gateway adapter for ESP32/SX127x JSON-line LoRa packets and documented first hardware bridge command | lora_gateway_serial.py; requirements.txt; simulation/README.md; Progress Tracker; Change Log | compileall passed | Pending commit | Build ESP32 gateway firmware packet output
C008 | 2026-05-15 | Firmware | Added dedicated ESP32 LoRa gateway firmware project that receives SX1278 packets, normalizes metadata, and emits one JSON packet per serial line | firmware/esp32-lora-gateway; lora_gateway_serial.py; Progress Tracker; Change Log | Python parser smoke test passed; PlatformIO not installed locally, so firmware compile not run | Pending commit | Add automated tests for LoRa parser/store APIs
C009 | 2026-05-15 | Tests | Added unittest coverage for LoRa serial parsing, SQLite packet dedupe/history, and simulator packet metrics | raspi/firenode-system/tests/test_lora_pipeline.py; scripts/run_raspi_tests.sh; Progress Tracker; Change Log | ./scripts/run_raspi_tests.sh: 4 tests OK | Pending commit | Implement camera recording on chainsaw event
C010 | 2026-05-15 | Recording | Added event recorder that saves chainsaw camera snapshots plus metadata and exposes /api/recordings | modules/event_recorder.py; app.py; tests/test_lora_pipeline.py; Progress Tracker; Change Log | ./scripts/run_raspi_tests.sh: 5 tests OK | Pending commit | Add dashboard recording list
C011 | 2026-05-15 | Dashboard | Added recent recordings panel and /media route so chainsaw snapshots can be reviewed in the web GUI | templates/dashboard.html; static/app.js; static/style.css; app.py; Progress Tracker; Change Log | ./scripts/run_raspi_tests.sh: 5 tests OK; / and /api/recordings returned 200 | Pending commit | Add CI workflow
C012 | 2026-05-15 | CI/CD | Added GitHub Actions workflow for Python app tests, compileall, and PlatformIO builds for sender and gateway firmware | .github/workflows/ci.yml; Progress Tracker; Change Log | ./scripts/run_raspi_tests.sh: 5 tests OK; PlatformIO unavailable locally | Pending commit | Add deployment/systemd scripts
C013 | 2026-05-15 | Deployment | Added systemd install/stop scripts for the LoRa serial gateway bridge and documented gateway service operations | install_lora_gateway_service.sh; stop_lora_gateway_service.sh; README.md; Progress Tracker; Change Log | bash -n scripts passed; ./scripts/run_raspi_tests.sh: 5 tests OK | Pending commit | Add API smoke-test script
C014 | 2026-05-15 | Testing | Added end-to-end simulation smoke test and wired it into CI | scripts/smoke_test_main_simulation.py; .github/workflows/ci.yml; Progress Tracker; Change Log | ./scripts/smoke_test_main_simulation.py passed | Pending commit | Add field deployment checklist/docs
C015 | 2026-05-15 | Deployment | Added field deployment checklist covering bench prep, node install, LoRa validation, camera/recording checks, alert validation, and shutdown | docs/deployment/field_deployment_checklist.md; Progress Tracker; Change Log | Documentation review | Pending commit | Add hardware wiring reference
C016 | 2026-05-15 | Hardware | Added wiring reference for ESP32 sensor sender, ESP32 LoRa gateway, main/remote Raspberry Pi devices, power notes, and open hardware decisions | docs/hardware/wiring_reference.md; Progress Tracker; Change Log | Documentation review | Pending commit | Add README links to new docs
C017 | 2026-05-15 | Documentation | Updated top-level README with fast start commands, current build path, and links to key project references | README.md; Progress Tracker; Change Log | Documentation review | Pending commit | Add release/package script
C018 | 2026-05-15 | Release | Added release packaging script that uses git archive to create a clean zip under dist | scripts/package_release.sh; Progress Tracker; Change Log | ./scripts/package_release.sh produced dist zip | Pending commit | Add packet schema documentation
C019 | 2026-05-15 | Documentation | Added LoRa sender payload, gateway serial line, ingest/history/status API, SQLite table, and validation target schema documentation | docs/api/lora_packet_schema.md; README.md; Progress Tracker; Change Log | Documentation review | Pending commit | Run full local verification
C020 | 2026-05-15 | Verification | Completed full local verification checkpoint after unblocked development steps | Progress Tracker; Change Log | ./scripts/run_raspi_tests.sh OK; ./scripts/smoke_test_main_simulation.py OK; python3 -m compileall OK; package_release produced dist/adm-firenode-192b1c7-20260514-141016.zip | Pending commit | Push to GitHub after remote is provided
C021 | 2026-05-15 | GitHub | Pushed project code, firmware, docs, and workbook to GitHub main; excluded CI workflow because token lacks workflow scope | Progress Tracker; Issue Log; GitHub Workflow; Change Log; workbook | git push to https://github.com/pagibetech/adm-firenode-forest-monitoring.git succeeded at commit 05e1a77 | 05e1a77 on GitHub | Enable workflow scope to push CI workflow later
C022 | 2026-05-15 | AI Workflow | Added hybrid low-cost AI workflow workbook sheets for model routing, active context, handoff, validation matrix, environment, logs, and continuation | Active Context Snapshot; AI Session Handoff; AI Stack; AI Router; AI Model Routing Log; Codex Task Log; Build Validation Matrix; Environment Snapshot; Prompt Library | Workbook rendered and formula scan clean | Pending commit | Use workbook + GitHub as persistent project memory
C023 | 2026-05-20 | Deployment | Added MacBook-run automated deployment scripts for the four Raspberry Pis with simulation-mode config, optional systemd service, manual start default, and beginner validation guide | scripts/deploy_main_server.sh; scripts/deploy_node.sh; scripts/deploy_all_rpis.sh; docs/deployment/rpi_automated_deployment.md; workflow memory docs | bash -n passed; deploy_node --help checked | Pending commit | Run deployment on live RPis and capture validation results
C024 | 2026-05-20 | Deployment | Updated RPi deployment automation for parallel default deployment, sequential mode, target-only mode, per-IP logs, pass/fail summary, and simulation role labels; recorded ESP32 hardware validation pause | scripts/deploy_all_rpis.sh; scripts/deploy_node.sh; scripts/deploy_main_server.sh; raspi/firenode-system/app.py; docs/deployment/rpi_automated_deployment.md; workflow docs; workbook | bash -n passed; help output checked; Python tests OK; smoke test OK | Pending commit | Run ./scripts/deploy_all_rpis.sh from MacBook
C025 | 2026-05-21 | Camera | Added configurable USB camera capture settings for live Raspberry Pi cameras: V4L2 backend, MJPG FOURCC, warmup frames, retry/reopen on failed reads, and RPi camera_test.py helper | raspi/firenode-system/modules/camera_stream.py; raspi/firenode-system/camera_test.py; raspi/firenode-system/app.py; raspi/firenode-system/config.json; docs; workbook | py_compile passed; unit tests OK; smoke test OK; camera_test.py --help OK | Pending commit | Deploy to main server and validate /dev/video0 live feed
C026 | 2026-05-21 | Camera | Lowered RPi 3B USB camera defaults to 320x240, 10 FPS, JPEG quality 55, MJPG, and 10 warmup frames after corrupt MJPG frame warnings | app.py; config.json; camera_stream.py; camera_test.py; static/app.js; docs; workbook | py_compile passed; unit tests OK; smoke test OK; camera_test.py --help OK; deploy scripts syntax OK | Pending commit | Deploy to main server and validate image clarity
C018 | 2026-06-02 | Documentation | Updated ACTIVE_CONTEXT, PROJECT_STATUS, AI_SESSION_HANDOFF, wiring_reference, field_deployment_checklist, and workbook with ESP32 MAIN + NODE_01 bench validation results | docs/ACTIVE_CONTEXT.md; docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; docs/hardware/wiring_reference.md; docs/deployment/field_deployment_checklist.md; docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx | Documentation review | Pending commit | Continue ESP32-to-RPi integration using MAIN + validated NODE_01 path
C027 | 2026-06-02 | Hardware | Finalized Raspberry Pi Camera Rev 1.3 CSI as official camera hardware; deprecated USB webcam | docs/ACTIVE_CONTEXT.md; docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; docs/hardware/wiring_reference.md; docs/deployment/field_deployment_checklist.md; workbook | Documentation review; rpicam-hello detection confirmed on .51/.52 | Pending commit | Implement rpicam/libcamera capture pipeline (P042)
C028 | 2026-06-02 | Hardware | .51 MAIN and .52 NODE_01 CSI camera detection confirmed (ov5647) | docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; workbook | rpicam-hello --list-cameras output recorded | Pending commit | Integrate rpicam/libcamera into camera_stream.py and validate stream endpoint
C027 | 2026-06-02 | Hardware | Finalized Raspberry Pi Camera Rev 1.3 CSI as official camera hardware; deprecated USB webcam | docs/ACTIVE_CONTEXT.md; docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; docs/hardware/wiring_reference.md; docs/deployment/field_deployment_checklist.md; workbook | Documentation review; rpicam-hello detection confirmed on .51/.52 | Committed | Implement rpicam/libcamera capture pipeline (P042)
C028 | 2026-06-02 | Hardware | .51 MAIN and .52 NODE_01 CSI camera detection confirmed (ov5647) | docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; workbook | rpicam-hello --list-cameras output recorded | Committed | Integrate rpicam/libcamera into camera_stream.py and validate stream endpoint
C029 | 2026-06-02 | Camera | Implemented modules/csi_camera_stream.py with Picamera2; updated multi_camera_stream.py, app.py, config, dashboard UI | modules/csi_camera_stream.py; modules/multi_camera_stream.py; app.py; config.json; requirements.txt; templates/dashboard.html; static/app.js | py_compile validation passed; CSI primary with USB fallback; simulation preserved | Pending commit | Deploy to .51/.52 and validate /video_feed endpoint
C039 | 2026-06-08 | Dashboard | MAIN .51 dashboard confirmed in LIVE mode with CSI camera and ESP32 serial integration | app.py; modules/csi_camera_stream.py; modules/esp32_serial_reader.py; config.json; templates/dashboard.html; static/app.js | Visual inspection on .51; rpicam-hello confirmed; minicom confirmed serial packets | Pending commit | Deploy to .51 and validate sensor cards populate from serial cache
C040 | 2026-06-08 | Hardware | CSI camera validation .51 PASS — MAIN .51 CSI camera works in LIVE mode | modules/csi_camera_stream.py; hardware/wiring_reference.md; docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md | rpicam-hello --list-cameras; dashboard visual inspection; curl /video_feed | Pending commit | Validate .52 NODE_01 camera feed on MAIN dashboard
C041 | 2026-06-08 | Hardware | CSI camera validation .52 PASS — NODE_01 .52 CSI camera works and appears on MAIN dashboard | modules/csi_camera_stream.py; multi_camera_stream.py; app.py; docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md | rpicam-hello on .52; dashboard remote camera grid inspection; /api/server-dashboard JSON | Pending commit | Validate remote node aggregation and sensor data sync
C042 | 2026-06-08 | Integration | Remote node aggregation .51 to .52 PASS — MAIN discovers and pulls NODE_01 data and camera feed | app.py; modules/node_registry.py; modules/network_utils.py; docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md | Dashboard inspection; network reachability; /api/server-dashboard remote slot 1 populated | Pending commit | Validate ESP32 serial reader live integration on .51
C043 | 2026-06-08 | Integration | MAIN ESP32 USB serial reader IMPLEMENTED / PENDING VERIFICATION — modules/esp32_serial_reader.py created and integrated | modules/esp32_serial_reader.py; app.py; config.json; docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; docs/hardware/wiring_reference.md; docs/deployment/field_deployment_checklist.md | python3 -m py_compile passed; parsing unit test passed; manual parse_line verification | Pending commit | Deploy to .51 MAIN and verify sensor cards populate from serial cache
C044 | 2026-06-08 | Hardware | MAIN ESP32 serial hardware manually confirmed using Minicom on /dev/ttyUSB0 at 115200 | docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md; docs/hardware/wiring_reference.md | Minicom session captured NODE=MAIN and NODE=NODE_01 packets | Pending commit | Deploy serial reader code and confirm dashboard overlay in LIVE mode
C045 | 2026-06-08 | Hardware | .53 NODE_02 and .54 NODE_03 marked pending hardware build — CSI cameras installed, ESP32 + sensors not assembled | docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md; docs/AI_SESSION_HANDOFF.md; docs/hardware/wiring_reference.md | Physical inventory status | Pending commit | Assemble NODE_02/NODE_03 using NODE_01 baseline and validate
C046 | 2026-06-08 | Hardware | Thermal camera retained as MAIN-only design component but marked pending physical installation | docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md; modules/thermal_camera.py | Design review; module exists in code; hardware not installed | Pending commit | Install MLX90640 on MAIN and validate /thermal_feed
C047 | 2026-06-08 | Audio | Chainsaw detection marked pending USB microphone installation and testing | detector.py; test_audio/; docs/PROJECT_STATUS.md; docs/ACTIVE_CONTEXT.md | Synthetic test audio exists; no live microphone hardware connected | Pending commit | Install USB microphone on a node and run live chainsaw detection validation
C048 | 2026-06-08 | Integration | Serial integration status consolidation — created 2026-06-08 Serial Update worksheet; MAIN/NODE_01 serial/camera/dashboard benchmarks recorded; serial reader implemented pending dashboard verification; .53/.54, thermal, chainsaw status noted | docs/workbook/ADM_FireNode_Implementation_Workbook.xlsx (new sheet: 2026-06-08 Serial Update) | py_compile; minicom serial capture; dashboard visual inspection; rpicam-hello camera detection | Pending commit | Complete serial dashboard integration verification on .51; do NOT mark serial dashboard as PASS yet
C049 | 2026-06-09 | Hardware | NODE_02 (.53) and NODE_03 (.54) CSI camera setup and validation completed | docs/ACTIVE_CONTEXT.md; docs/PROJECT_STATUS.md; docs/AI_SESSION_HANDOFF.md; docs/deployment/field_deployment_checklist.md; docs/ROO_HANDOFF_PROMPT.md; workbook | Visual inspection on .53/.54 dashboards; rpicam-hello --list-cameras; curl /video_feed; /api/node-data camera_type=csi | Pending commit | Resume MAIN ESP32 serial verification when .51 is reachable

## 2026-06-08 Serial Update
Serial Integration Status — 2026-06-08
Hardware bench status for MAIN (.51) and NODE_01 (.52) serial, camera, and dashboard integration.
# | Category | Item | Status | Details
1 | Dashboard | MAIN .51 dashboard LIVE mode | CSI CAMERA VALIDATED | CSI cameras physically mounted and operational on .53/.54; live stream confirmed on local dashboards; ESP32 + LoRa + sensor modules not yet assembled.
2 | Camera | MAIN .51 CSI camera | PASS | ov5647 CSI camera confirmed via rpicam-hello; clear and stable feed on dashboard.
3 | Camera | NODE_01 .52 CSI camera | PASS | ov5647 CSI camera confirmed; feed visible in MAIN dashboard remote-camera grid.
4 | Integration | Remote node aggregation .51 to .52 | PASS | MAIN discovers NODE_01 via zeroconf/mDNS; remote slot 1 populated with sensor + camera data.
5 | Hardware | .53 NODE_02 / .54 NODE_03 | PENDING BUILD | CSI cameras physically mounted; ESP32 + LoRa + sensor modules not yet assembled.
6 | Hardware | Thermal camera (MLX90640) | NOT INSTALLED | MAIN-only design component; module exists in code but hardware not on bench.
7 | Audio | USB microphone / chainsaw detection | PENDING | detector.py + synthetic test audio exist; no USB microphone connected on any node.
8 | Hardware | MAIN ESP32 ↔ RPi serial link | CONFIRMED | ESP32 connected via /dev/ttyUSB0 at 115200 baud; minicom shows readable packets.
9 | Validation | Minicom serial packet capture | PASS | Packets from NODE=MAIN and NODE=NODE_01 observed; JSON-Line format confirmed.
14 | Camera | NODE_02 .53 CSI camera | PASS | ov5647 CSI camera confirmed via rpicam-hello; clear and stable feed on local dashboard; required python3-picamera2 and file sync.
15 | Camera | NODE_03 .54 CSI camera | PASS | ov5647 CSI camera confirmed via rpicam-hello; clear and stable feed on local dashboard; required python3-picamera2 and sync of modules/multi_camera_stream.py from NODE_01.
16 | Software | Serial dashboard integration | PENDING VERIFICATION | Code deployed to .51; LIVE sensor-card population from serial cache NOT YET VERIFIED. Blocked by .51 unavailability.
13 | Firmware | ESP32 LoRa gateway firmware | PASS | LoRa RX two-way MAIN ↔ NODE_01 validated (RSSI -29 to -35 dBm; SNR 9.25-10.00).